# PROPOSAL FOR APPROVAL UNDER SAMAGRA SHIKSHA

Government of Karnataka

Effectiveness of In-service Teacher Training in Karnataka (2021-2026): From Training Hall to Classroom

| Name of the State | Karnataka |
| --- | --- |
| Title of the proposal | Effectiveness of In-service Teacher Training in Karnataka (2021-2026): From Training Hall to Classroom |
| Scheme and component | Samagra Shiksha: Teacher Education (research and evaluation by SCERT and DIETs) |
| Implementing agency | Department of State Educational Research and Training (DSERT), Karnataka, with 30 District Institutes of Education and Training (DIETs) |
| Nodal officer | Senior Assistant Director (Teacher Education and Research), DSERT, Bengaluru |
| Period evaluated | 2021-22 to 2025-26 |
| Duration of the study | 18 months (Month 1 to Month 18) |
| Coverage | Four clusters of in-service training; 30 DIET districts; about 3,000 teachers in 600 schools; 600 classrooms observed twice; about 9,000 students |
| Total cost | ₹1,28,44,125 (Year 1: ₹1,06,44,375; Months 13-18: ₹21,99,750) |
| Central share (60%) / State share (40%) | ₹77,06,475 / ₹51,37,650 |

# Summary

Karnataka trains a large number of teachers every year under Samagra Shiksha, but it records only attendance and expenditure. It does not know whether teachers use what they learn, whether their schools help them to do so, or whether students gain. This study follows four clusters of training (subject packages, child protection and safety, ICT, and partnership trainings) from the training hall into 600 classrooms in 30 DIET districts. It uses Guskey’s five levels of professional development evaluation, observes each classroom twice to test whether change lasts, links teaching practice to the learning of about 9,000 students, and estimates the cost of each unit of practice change. It will give the State a tested framework for planning training load, sequence, mode and follow-up, and tools that DIETs can reuse. The cost is ₹1.28 crore over 18 months, shared 60:40 between the Centre and the State.

# 1. Background

Over the last five years Karnataka has trained tens of thousands of teachers every year through subject packages, child protection and safety orientation, ICT courses and partnership programmes. Progress reports record how many teachers attended and how much was spent. They do not record whether teachers use what they learned, whether schools support them to do so, or whether students benefit.

This study follows training from the training hall into the classroom. For each of four clusters of training, it asks whether teachers valued the training, learned from it, were supported to apply it and changed their practice, whether students gained, and at what cost.

# 2. Scope: four clusters of training

| Cluster | Trainings covered | Evidence of use expected |
| --- | --- | --- |
| A. Subject and learning-programme packages (Samagra Shiksha grant; about 95,000 teachers) | Jana Sethu, Kalika Deepa, Read Karnataka (Odu Karnataka), Ganitha Ganaka, Maru Sinchana, Content Enrichment, Math Learning Camp | Specific teaching strategies in class; student learning in Grades 3, 5 and 8 |
| B. Child protection and safety | POCSO, Child Rights, Road Safety | Teachers’ knowledge of procedures; safety measures in the school; students’ awareness |
| C. ICT | TALP induction (18,600 teachers), TALP refresher (2,000 teachers), Digital Library training | Use of ICT and digital content in teaching; working ICT facilities; usage records |
| D. Partnership and special trainings | 10,000 teachers trained with Azim Premji Foundation (APF); teachers of bilingual schools (EMTIP) | Depth of practice change; language use and learning in bilingual classes |

Trainings that had not reached all intended teachers by the time of fieldwork provide a natural comparison group of teachers not yet trained.

# 3. Rationale and need

- Scale of investment. In-service training is one of the largest recurring items in the State’s Samagra Shiksha plan, yet its effect on classrooms has not been measured.

- Choices the State must make. The next PAB proposal and the State training calendar need evidence on how much training teachers can absorb, in what order, by which mode and with what follow-up.

- Competing delivery models. The departmental cascade (State to Master Resource Person to teacher) and the APF model of direct, sustained engagement have run side by side. Their relative effect and cost are not known.

- Different kinds of training need different evidence. Subject training should change teaching and learning; awareness training should change knowledge, procedures and school safety. The study judges each against its own purpose.

# 4. Relationship with the companion proposal

DSERT is submitting a second proposal, Teacher Education and School Quality Initiatives in Karnataka (2021-2026): An Integrated Evaluation of Investment, Practice and Outcomes. The two studies are designed to complement each other, not to duplicate.

|  | This study (training effectiveness) | Companion study (integrated evaluation) |
| --- | --- | --- |
| Main question | Does each cluster of training change practice and learning, and why? | Was the State’s training investment well planned, funded, delivered and spread? |
| Unit of analysis | Individual teacher, classroom and student | Programme, fund source and district |
| Distinctive evidence | Module-linked knowledge tests; repeat observation after three months; student learning tasks; school safety audit; cost per unit of practice change | Reconciled financial database; unique-teacher reach; fund-flow bottlenecks; district-level outcome analysis |
| Learning (Kirkpatrick/Guskey level 2) | Measured by tests | Self-reported |

To avoid duplicate fieldwork, the two studies will share the training records extracted from Samagra Shiksha Karnataka and will not sample the same schools. The Steering Committee will review both studies together.

# 5. Alignment with national and State policy

| Document | Relevance |
| --- | --- |
| NEP 2020 | At least 50 hours of continuous professional development a year for every teacher; need-based, teacher-led training |
| Samagra Shiksha framework and norms | In-service training, induction, ICT, and the role of DIETs in research and evaluation |
| NIPUN Bharat Mission | Foundational literacy and numeracy, the focus of several Cluster A packages |
| NCF-SE 2023 | Competency-based pedagogy that subject training aims to build |
| POCSO Act, 2012 and the Right of Children to Free and Compulsory Education Act, 2009 | Duties of schools on child protection, and the prohibition of corporal punishment |
| PARAKH Rashtriya Sarvekshan 2024 | Learning outcome data for district comparisons |

# 6. Objectives

- To assess teachers’ reaction to, and learning from, each cluster of training.

- To assess the support that head teachers, CRPs, BRPs and school resources give teachers to apply their training.

- To assess whether classroom practice changed, and whether the change lasts about three months later.

- To examine whether student learning, attendance or safety improved where teachers applied their training.

- To compare delivery models, package and standalone training, and modes of delivery.

- To estimate the cost per teacher per unit of practice change for each cluster and delivery model.

- To develop a Karnataka Teacher Training Effectiveness Framework and recommendations on training load, sequencing, mode and follow-up.

# 7. Evaluation framework: Guskey’s five levels

The study uses Thomas Guskey’s five levels of professional development evaluation. The framework suits teacher training because it includes a level for organisational support: whether the school helps teachers apply what they learned. Cost-effectiveness is examined alongside as a sixth question.

| Level | Question | Main evidence |
| --- | --- | --- |
| 1. Reaction | Did teachers find the training relevant and well delivered? | Teacher survey; training-quality checklist; resource-person feedback |
| 2. Learning | Did their knowledge and skills improve? | Module-linked knowledge tests; pre- and post-test scores from training records |
| 3. Organisational support | Did head teachers, CRPs, BRPs and school resources help them apply it? | Head teacher and CRP/BRP questionnaire; school resources checklist |
| 4. Use | Did classroom practice change, and does the change last? | Classroom observation at fieldwork and about three months later; school safety audit |
| 5. Student outcomes | Did learning, attendance or safety improve? | Student learning tasks; attendance records; safety audit; PARAKH and State data |
| Cost-effectiveness | What is the cost per teacher per unit of practice change? | Cost sheets; Samagra Shiksha expenditure; effect sizes |

Indicators by level and cluster

| Level | A. Subject packages | B. Child protection | C. ICT | D. Partnership |
| --- | --- | --- | --- | --- |
| Reaction | Relevance to syllabus and grade | Clarity of procedures | Hands-on time on devices | Depth and follow-up |
| Learning | Module test on strategies | Test on POCSO reporting, child rights and road safety rules | TALP skills test | Test on APF or bilingual teaching strategies |
| Support | Materials, CRP visits, time in the timetable | Head teacher action; committee in place | Working devices, power, connectivity | Mentor and peer support |
| Use | Package strategies seen in class | Safety measures and displays; referral procedure known | ICT and Digital Library used in lessons | Quality of practice; language use in class |
| Student outcomes | Grade 3, 5 and 8 learning tasks | Students’ awareness of safety and of whom to tell | Students’ use of digital content | Learning; bilingual proficiency |

# 8. Research questions

Cross-cutting

- RQ1. At which Guskey level does the effect of training weaken most, for each cluster?

- RQ2. Does organisational support explain why some trained teachers use their training and others do not?

- RQ3. Does practice change last about three months after fieldwork?

- RQ4. What is the cost per teacher per unit of practice change, by cluster and delivery model?

Cluster A: Subject and learning-programme packages

- RQ5. Which package strategies do trained teachers use in class, and how faithfully?

- RQ6. Do students of teachers with higher fidelity score higher on Grade 3, 5 and 8 learning tasks?

- RQ7. Does package training (several programmes in one block) lead to more use than standalone training?

- RQ8. How much content is lost as the cascade passes from State resource persons to MRPs to teachers?

Cluster B: Child protection and safety

- RQ9. Do teachers know the POCSO reporting procedure, children’s rights and road safety rules?

- RQ10. Have trained schools put the required safety measures in place?

- RQ11. Do students know how to stay safe and whom to tell?

Cluster C: ICT

- RQ12. Do TALP-trained teachers use ICT and the Digital Library in lessons, and how often?

- RQ13. How far do working equipment and connectivity limit use?

- RQ14. Does the TALP refresher add to use beyond induction?

Cluster D: Partnership and special trainings

- RQ15. Does the APF direct model produce greater and more lasting practice change than the departmental cascade, and at what cost?

- RQ16. Do EMTIP-trained teachers use bilingual strategies, and how do students in bilingual classes perform?

# 9. Key comparisons

| Comparison | How it is made |
| --- | --- |
| Cascade and direct delivery | Teachers trained through the departmental cascade compared with APF-trained teachers, matched on subject, grade, experience and school type |
| Package and standalone training | Teachers who received Cluster A trainings as a combined package compared with those who received them separately |
| Delivery mode | Face-to-face, blended, and DIET studio-based or online delivery compared at each Guskey level |
| Trained and not-yet-trained; amount of training | Trained and not-yet-trained teachers compared; dose-response by hours and number of trainings |
| Subject and awareness training | Clusters A and D judged on practice and learning; Clusters B and C judged on knowledge, procedures, school measures and use |

# 10. Design and methodology

## 10.1 Approach

The study uses mixed methods with three strands:

- a tracer study that follows trained teachers from training records into their schools and classrooms;

- a quasi-experimental comparison of teachers with different training exposure; and

- case studies of strong and weak cases.

## 10.2 Sample

All 30 DIET districts are covered. In each district about 100 teachers are drawn from 20 schools. Teachers are selected from the training MIS by stratified random sampling on training exposure, so that each cluster, the APF and EMTIP groups, and not-yet-trained teachers are adequately represented.

| Unit | Per district | State total | Selection |
| --- | --- | --- | --- |
| Schools | 20 | 600 | Stratified random, by rural or urban location and by school level |
| Teachers | About 100 | About 3,000 | Stratified by training exposure from the training MIS |
| Classrooms observed | 20 | 600, each observed twice | One teacher per school, chosen to cover all four clusters |
| Students assessed | About 300 | About 9,000 | About 15 per observed class, in Grades 3, 5 and 8 |
| Head teachers | 20 | 600 | All sampled schools |
| CRPs and BRPs | About 7 | About 210 | All serving the sampled schools |
| Live training sessions observed | 2 | 60 | Trainings running during fieldwork |
| Focus group discussions | 2 | 60 | One with teachers; one with resource persons |
| In-depth interviews | 5 | 150, plus 10 with APF and EMTIP staff | DIET Principal, BEO, BRP, resource person, head teacher |
| Case studies | - | 16 | A strong and a weak case for each of two settings in each cluster |

APF and EMTIP strata are drawn only in the districts where those programmes ran; elsewhere the places are reallocated to Clusters A to C.

Sampling rules. The observed teacher in each school is drawn from those teaching Grade 3, 5 or 8, so that student tasks can be linked to observed practice. Where a sampled school has too few eligible teachers, a replacement school is drawn from the same stratum, and all replacements are recorded. The inception report will include a power calculation for the main comparisons, using intra-class correlations estimated from the pilot, and will adjust strata sizes if needed within the approved budget.

## 10.3 Tools

- Training-quality checklist and resource-person feedback form, used in 60 live sessions.

- Teacher knowledge tests, one linked to each module.

- Classroom observation schedule, with common indicators and cluster-specific indicators.

- Head teacher and CRP/BRP support questionnaire.

- Student learning tasks for Grades 3, 5 and 8 in Kannada, English and Mathematics.

- School safety audit for POCSO and road safety measures.

- Cost sheets for each training, covering resource persons, venue, travel, materials and teacher time.

All tools will be piloted in 10 schools outside the sample and finalised before fieldwork.

## 10.4 Records used

Training MIS and attendance data; TALP data; pre- and post-test scores from the trainings themselves; Samagra Shiksha expenditure; PARAKH Rashtriya Sarvekshan 2024 and State assessment data.

## 10.5 Analysis

- Descriptive analysis of each Guskey level by cluster, district and delivery mode.

- Quasi-experimental comparison of trained and not-yet-trained teachers using propensity score matching.

- Dose-response analysis relating hours and number of trainings to practice.

- Multilevel models of students within classrooms within schools within districts, linking practice to learning.

- Durability: change in observed practice between fieldwork and follow-up.

- Cost-effectiveness: cost per teacher per 0.1 standard deviation of practice change, by cluster and delivery model.

- Qualitative analysis of FGDs, interviews and case studies by Guskey level, with double coding of 10 per cent of transcripts.

## 10.6 The main challenge: overlapping trainings

Many teachers attended several of these trainings in the same period, so the effect of a single training cannot be fully separated. The design deals with this in two ways. First, it compares teachers who received different combinations and amounts of training. Second, it uses a module-practice map: each observation indicator is linked to the module that taught it, so that a change in that practice can be traced to that module rather than to training in general.

# 11. Implementation strategy and institutional arrangement

- State level (DSERT): a Principal Investigator, two Research Associates, a statistician and a data assistant. A Steering Committee chaired by the Director, DSERT, meets every quarter. A Technical Advisory Committee includes experts in teacher education, evaluation, assessment and statistics, and a representative of APF.

- District level (30 DIETs): the DIET Principal is the nodal officer, one faculty member is the District Coordinator, and two certified investigators work in each district. DIETs prepare the district training-impact profiles.

- Convergence: Samagra Shiksha Karnataka for the training MIS and expenditure; the TALP programme for ICT data; APF and the EMTIP programme for partnership data.

# 12. Action plan

| Phase | Months | Activity | Responsibility | Deliverable |
| --- | --- | --- | --- | --- |
| 1. Tools and pilot | M1 | Constitute committees; orient 30 DIET Principals and coordinators | DSERT | Committee orders |
|  | M1-M3 | Extract training MIS, attendance, TALP and expenditure records | State team; Samagra Shiksha Karnataka | Linked records |
|  | M1-M2 | Develop tools and the module-practice map | State team; subject experts | Draft tools |
|  | M2-M3 | Ethics clearance; training of trainers; investigator certification | State team; DIETs | 60 certified investigators |
|  | M3 | Pilot in 10 schools outside the sample; finalise tools; power calculation | DIETs; State team | Inception report (M3) |
| 2. Fieldwork | M4 | Draw the teacher sample by training exposure | State team | Sample list |
|  | M4-M7 | Teacher survey and knowledge tests for about 3,000 teachers | DIETs | Teacher dataset |
|  | M5-M8 | Observe 600 classrooms; student tasks; head teacher and CRP/BRP questionnaires; safety audit | DIETs | School dataset |
|  | M4-M9 | Observe 60 live trainings; 60 FGDs; 160 interviews | DIETs; State team | Fieldwork report (M9) |
| 3. Follow-up | M10-M12 | Re-observe the same 600 classrooms; 16 case studies | DIETs; State team | Follow-up report (M12) |
| 4. Analysis | M13-M15 | Analysis by Guskey level and cluster; cost-effectiveness | State team; statistician | Analysis tables |
|  | M15-M16 | DIETs prepare 30 district training-impact profiles | DIETs | District profiles |
| 5. Report | M16-M17 | Divisional and State validation workshops | DSERT; DIETs | Agreed recommendations |
|  | M16-M18 | Final report and Karnataka Teacher Training Effectiveness Framework | State team | Final report (M18) |
| Throughout | M1-M18 | Quarterly Steering Committee; monitoring visits | DSERT | Minutes; monitoring reports |

# 13. Gantt chart

Milestone reports: M3 inception report; M9 fieldwork report; M12 follow-up report; M18 final report. If required, the study can be completed in 15 months by reducing analysis and reporting to three months.

# 14. Budget

The total cost of the study is ₹1,28,44,125 (Rupees One Crore Twenty-Eight Lakh Forty-Four Thousand One Hundred and Twenty-Five only) for 18 months: ₹1,06,44,375 in Year 1 (Months 1-12) and ₹21,99,750 in Months 13-18. Unit costs are indicative and will be finalised against the Samagra Shiksha norms in force at the time of approval.

Summary of budget by head (₹)

| Budget head | Year 1 | Months 13-18 | Total | Share |
| --- | --- | --- | --- | --- |
| A. Personnel | 19,80,000 | 8,40,000 | 28,20,000 | 22.0% |
| B. Field data collection | 42,15,000 | - | 42,15,000 | 32.8% |
| C. Travel and daily allowance | 18,60,000 | 75,000 | 19,35,000 | 15.1% |
| D. Training, meetings and workshops | 7,52,500 | 7,40,000 | 14,92,500 | 11.6% |
| E. Tools, technology, printing and ethics | 13,30,000 | - | 13,30,000 | 10.4% |
| F. Reporting and dissemination | - | 4,40,000 | 4,40,000 | 3.4% |
| G. Contingency and administration (5%) | 5,06,875 | 1,04,750 | 6,11,625 | 4.8% |
| Grand total | 1,06,44,375 | 21,99,750 | 1,28,44,125 | 100.0% |

Detailed budget (₹)

| No. | Head | Item | Unit cost and quantity | Year 1 | Months 13-18 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | A | State Research Associates | 2 × 30,000 × 18 months | 7,20,000 | 3,60,000 | 10,80,000 |
| 2 | A | Statistician / data analyst | 1 × 35,000 × 18 months | 4,20,000 | 2,10,000 | 6,30,000 |
| 3 | A | Data assistant (training MIS, TALP and expenditure records) | 1 × 25,000 × 12 months | 3,00,000 | - | 3,00,000 |
| 4 | A | District Coordinators (DIET faculty honorarium) | 30 × 1,500 × 18 months | 5,40,000 | 2,70,000 | 8,10,000 |
| 5 | B | Fieldwork investigator days | 600 schools × 2 investigators × 2 days × 1,000 | 24,00,000 | - | 24,00,000 |
| 6 | B | Follow-up classroom observation | 600 classrooms × 1 day × 1,000 | 6,00,000 | - | 6,00,000 |
| 7 | B | Observation of live training sessions | 60 sessions × 2,000 | 1,20,000 | - | 1,20,000 |
| 8 | B | Teacher knowledge tests: printing and scoring | 3,000 teachers × 30 | 90,000 | - | 90,000 |
| 9 | B | Student learning tasks (Grades 3, 5, 8): printing and scoring | 9,000 students × 25 | 2,25,000 | - | 2,25,000 |
| 10 | B | FGD facilitation and refreshments | 60 FGDs × 3,000 | 1,80,000 | - | 1,80,000 |
| 11 | B | Transcription and translation | 220 FGDs and IDIs × 2,000 | 4,40,000 | - | 4,40,000 |
| 12 | B | Case studies of strong and weak cases | 16 × 10,000 | 1,60,000 | - | 1,60,000 |
| 13 | C | Investigator travel, fieldwork | 600 schools × 1,500 | 9,00,000 | - | 9,00,000 |
| 14 | C | Investigator travel, follow-up | 600 schools × 750 | 4,50,000 | - | 4,50,000 |
| 15 | C | State team monitoring visits | 30 districts × 2 visits × 6,000 | 3,60,000 | - | 3,60,000 |
| 16 | C | District Coordinators to State review meetings | 30 × 3 meetings × 2,500 | 1,50,000 | 75,000 | 2,25,000 |
| 17 | D | State-level training of trainers for District Coordinators | 45 participants × 3 days × 1,500 | 2,02,500 | - | 2,02,500 |
| 18 | D | District investigator training and observer certification | 30 × 15,000 | 4,50,000 | - | 4,50,000 |
| 19 | D | Steering and Technical Advisory Committee meetings | 6 × 25,000 | 1,00,000 | 50,000 | 1,50,000 |
| 20 | D | DIET workshops to prepare district training-impact profiles | 30 × 10,000 | - | 3,00,000 | 3,00,000 |
| 21 | D | Divisional validation workshops | 4 × 60,000 | - | 2,40,000 | 2,40,000 |
| 22 | D | State validation and dissemination workshop | 1 × 1,50,000 | - | 1,50,000 | 1,50,000 |
| 23 | E | Tablets (retained by DIETs) | 30 × 15,000 | 4,50,000 | - | 4,50,000 |
| 24 | E | Mobile data allowance | 60 investigators × 500 × 9 months | 2,70,000 | - | 2,70,000 |
| 25 | E | Tool development (module-linked tests, cluster indicators, learning tasks) and pilot | Lump sum | 2,50,000 | - | 2,50,000 |
| 26 | E | Database linking training MIS, TALP and field data | Lump sum | 1,00,000 | - | 1,00,000 |
| 27 | E | Printing of tools, consent and assent forms | Lump sum | 1,50,000 | - | 1,50,000 |
| 28 | E | Qualitative analysis software | Lump sum | 60,000 | - | 60,000 |
| 29 | E | Ethics review | Lump sum | 50,000 | - | 50,000 |
| 30 | F | Report writing, editing, design and printing | 500 copies | - | 3,00,000 | 3,00,000 |
| 31 | F | Effectiveness Framework, policy brief and 30 district profiles: printing | 30 × 3,000 + 50,000 | - | 1,40,000 | 1,40,000 |
| 32 | G | Contingency and administration | 5% of sub-total | 5,06,875 | 1,04,750 | 6,11,625 |
|  |  | Grand total |  | 1,06,44,375 | 21,99,750 | 1,28,44,125 |

Funding pattern (₹)

Karnataka falls under the 60:40 Centre-State sharing pattern of Samagra Shiksha.

| Period | Central share (60%) | State share (40%) | Total |
| --- | --- | --- | --- |
| Year 1 | 63,86,625 | 42,57,750 | 1,06,44,375 |
| Months 13-18 | 13,19,850 | 8,79,900 | 21,99,750 |
| Total | 77,06,475 | 51,37,650 | 1,28,44,125 |

Proposed release. Funds are sought in phases linked to milestones: the first release on approval; later releases on acceptance of the inception report (M3), the fieldwork report (M9) and the follow-up report (M12), together with utilisation certificates.

# 15. Monitoring and review

- Quarterly Steering Committee reviews of progress and expenditure.

- Two monitoring visits by the State team to each district; back-checks of 10 per cent of records and double observation in 10 per cent of classrooms.

- Quarterly physical and financial progress reports to Samagra Shiksha Karnataka; utilisation certificates as per scheme norms.

# 16. Ethics

- Ethics clearance before fieldwork (by Month 3).

- Informed consent from teachers, head teachers and officials; parental consent and child assent for student tasks.

- Observation and test results are used for evaluation only. They are not shared with supervisors or used for appraisal.

- Student questions on safety are general and age-appropriate; no child is asked about personal experience. Any disclosure is handled through the school’s child protection procedure.

- Data are pseudonymised after linkage and handled under the Digital Personal Data Protection Act, 2023.

# 17. Risks and mitigation

| Risk | Mitigation |
| --- | --- |
| Overlapping trainings blur the effect of any one training | Comparison by combination and amount of training; module-practice map |
| Training records incomplete or not linked to teacher IDs | Early extraction; matching on ID, name and school; match rate reported |
| Few not-yet-trained teachers in some districts | Comparisons pooled at division level; dose-response analysis |
| Teachers change their practice when observed | Research-only use made clear; first 10 minutes not scored; follow-up observation |
| Partner data not available | Data-sharing agreements with APF and EMTIP before fieldwork |
| Overlap with the companion study | Shared training records; separate school samples; joint review by the Steering Committee |
| Delay in release of funds | Phase-wise release; 5 per cent contingency |

# 18. Expected outputs

- An evidence-based Karnataka Teacher Training Effectiveness Framework.

- Recommendations on training load, sequencing, delivery mode and follow-up support.

- Inputs for the next PAB proposal and the State training calendar.

- 30 district training-impact profiles prepared by the DIETs.

- A comparison of the cost-effectiveness of clusters and delivery models.

- Validated tools (module tests, observation schedule, safety audit) that DIETs can reuse to evaluate future training.

# 19. Limitations

Teachers were not assigned to training at random, so the comparisons are quasi-experimental. Overlapping trainings limit how far the effect of a single training can be separated. Student outcomes are measured once, so links between practice and learning are associations. Findings apply to Government schools in the 30 DIET districts.

# 20. Certificate

Certified that the proposed study does not duplicate any activity approved for the State under Samagra Shiksha or any other scheme of the Government of India; that it has been designed to complement, and not to repeat, the companion proposal submitted by DSERT; that the costs have been worked out as per scheme norms; and that the funds will be used only for the purpose for which they are sanctioned.

Director
Department of State Educational Research and Training
Bengaluru

# Annexure: References

- Guskey, T. R. (2000). Evaluating Professional Development. Thousand Oaks, CA: Corwin Press.

- Guskey, T. R. (2002). Does it make a difference? Evaluating professional development. Educational Leadership, 59(6), 45-51.

- Ministry of Education (2020). National Education Policy 2020. Government of India.

- Ministry of Education. Samagra Shiksha: Framework for Implementation. Government of India.

- Ministry of Education (2021). NIPUN Bharat Guidelines. Government of India.

- NCERT (2023). National Curriculum Framework for School Education 2023. New Delhi: NCERT.

- NCERT. PARAKH Rashtriya Sarvekshan 2024. New Delhi: NCERT.

- Government of India. Protection of Children from Sexual Offences Act, 2012; Right of Children to Free and Compulsory Education Act, 2009; Digital Personal Data Protection Act, 2023.