# PROPOSAL FOR APPROVAL UNDER SAMAGRA SHIKSHA

Government of Karnataka

Teacher Education and School Quality Initiatives in Karnataka (2021-2026): An Integrated Evaluation of Investment, Practice and Outcomes

| Name of the State | Karnataka |
| --- | --- |
| Title of the proposal | Teacher Education and School Quality Initiatives in Karnataka (2021-2026): An Integrated Evaluation of Investment, Practice and Outcomes |
| Scheme and component | Samagra Shiksha: Teacher Education (research and evaluation by SCERT and DIETs) |
| Implementing agency | Department of State Educational Research and Training (DSERT), Karnataka, with the 34 District Institutes of Education and Training (DIETs) |
| Nodal officer | Senior Assistant Director (Teacher Education and Research), DSERT, Bengaluru |
| Period evaluated | 2021-22 to 2025-26 (five years) |
| Duration of the study | 18 months (Month 1 to Month 18) |
| Coverage | All in-service teacher training programmes under Samagra Shiksha and allied grants; field study in 408 Government schools across 34 educational districts; 1,224 teachers |
| Total cost | ₹96,01,200 (Year 1: ₹76,55,550; Months 13-18: ₹19,45,650) |
| Central share (60%) / State share (40%) | ₹57,60,720 / ₹38,40,480 |

# Summary

Between 2022-23 and 2025-26 the State’s progress records show a combined financial target of ₹5,493 lakh for in-service teacher training and recorded expenditure of ₹3,340 lakh. The records count teachers trained and money spent, but they do not show whether training reached the teachers who needed it, changed classroom practice or improved learning, or why several approved trainings were never held. This evaluation brings all programmes from 2021-22 to 2025-26 into one reconciled database, counts unique teachers reached, studies practice in 816 classrooms across all 34 educational districts, relates training intensity to district learning outcomes, and identifies bottlenecks in fund flow. It leaves DSERT with a database and dashboard that can be updated every year. The cost is ₹96.01 lakh over 18 months, shared 60:40 between the Centre and the State.

# 1. Background

Between 2021-22 and 2025-26, Karnataka has run a large programme of in-service teacher training under Samagra Shiksha, supported by allied grants. It includes NISHTHA online courses; induction training for newly recruited teachers; subject-wise training for high school teachers; foundational literacy and numeracy programmes (Odu Karnataka, Ganitha Ganaka, Kalika Deepa); the Marusinchana and Jnana Setu programmes; training with the Indian Institute of Science (IISc); the Guruchetana module; and orientation on child protection (POCSO), eradication of corporal punishment, value education and career counselling.

These programmes are monitored through physical and financial progress reports: how many teachers were trained against the target, and how much was spent against the allocation. The reports do not show whether training changed what teachers do in classrooms, or whether students learned more as a result. After five years of investment, and as the State prepares its plans for the next phase of Samagra Shiksha, an integrated evaluation is due.

# 2. What the progress records show

The State’s progress records for 2022-23 to 2025-26 report a combined financial target of ₹5,493 lakh for in-service teacher training, against recorded expenditure of ₹3,340 lakh (61 per cent). For 2025-26 the target shown is the first instalment only, as on 31.03.2026. Programme-wise details are at Annexure I. The records available for this proposal begin in 2022-23; records for 2021-22 will be compiled in Component 1.

| Year | Teachers targeted | Teachers trained | Financial target (₹ lakh) | Expenditure (₹ lakh) | Expenditure as % of target |
| --- | --- | --- | --- | --- | --- |
| 2022-23 | 1,12,423* | 1,51,659* | 1,116.05 | 842.98 | 75.5% |
| 2023-24 (two programmes reported) | 10,300 | 10,373 | 290.00 | 277.10 | 95.6% |
| 2024-25 | 1,20,316 | 1,08,353 (90.1%) | 1,561.05 | 1,291.62 | 82.7% |
| 2025-26 (as on 31.03.2026; first instalment) | See Annexure I | See Annexure I | 2,526.23 | 928.38 | 36.7% |

* 2022-23 includes NISHTHA online course completions, which exceed the target (184.9 per cent for primary teachers) and may count course enrolments rather than individual teachers.

Patterns that call for evaluation

- Falling utilisation. Expenditure in 2025-26 was 37 per cent of the first-instalment target and 62 per cent of the funds released to districts (₹928.38 lakh spent of ₹1,490.69 lakh released).

- Approved trainings not started. By 31.03.2026 no expenditure was recorded for content enrichment training (67,679 Government and aided school teachers targeted), Ganitha Kalika Andolana (25,891 teachers), Odu Karnataka one-day training (23,010 teachers), State-level Nali-Kali MRP training, BRP/ECO training, or training of educational administrators.

- Groups with low reach. Adivasi residential school teachers (155 of 592, 26 per cent) and high school teachers in the six-day 2025-26 package (18,491 of 44,218, 42 per cent).

- Low spending on some programmes. NIPUN Karnataka training in 2022-23 (28 per cent of the allocation) and Marusinchana for Classes 6-7 in 2024-25 (52 per cent).

- Strong performers. Subject-wise training for Classes 9-10 in 2023-24 (96 per cent of funds used), PAB-approved in-service training for Classes 6-8 in 2024-25 (97 per cent), and the Odu Karnataka-Ganitha Ganaka package in 2025-26 (96 per cent of teachers reached).

- Data quality. Several reported percentages do not match the underlying figures, and one programme records spending above the funds released (Annexure II).

# 3. Rationale and need

The State needs to know which of its teacher education investments change classroom practice and learning, at what cost, and why some programmes do not reach their targets. Progress reports answer only the first link in that chain.

| Question the State needs answered | What is available now | What this evaluation adds |
| --- | --- | --- |
| How much was invested, where and on what? | Year-wise physical and financial reports, in different formats | One reconciled database, 2021-22 to 2025-26, by programme, level, fund source and district |
| Who was reached, and who was missed? | Counts of participants against targets | Unique teachers reached, repeat training, groups left out, and progress towards 50 hours of CPD a year |
| Was the training good and relevant? | Not assessed | Teacher and resource-person feedback; review of design, cascade and timing |
| Did classroom practice change? | Not assessed | Observation of 816 classrooms, compared by training exposure |
| Did learning improve? | NAS, PARAKH and SSLC results, not linked to training | District-level linkage of training intensity to learning outcomes |
| Was it value for money? | Not assessed | Cost per teacher, per training day and per unit of observed change |

# 4. Relationship with the companion proposal

DSERT is submitting a second proposal, Effectiveness of In-service Teacher Training in Karnataka (2021-2026): From Training Hall to Classroom. The two studies are designed to complement each other, not to duplicate.

|  | This study (integrated evaluation) | Companion study (training effectiveness) |
| --- | --- | --- |
| Main question | Was the State’s training investment well planned, funded, delivered and spread? | Does each cluster of training change practice and learning, and why? |
| Unit of analysis | Programme, fund source and district | Individual teacher, classroom and student |
| Distinctive evidence | Reconciled financial database; unique-teacher reach; fund-flow bottlenecks; district-level outcome analysis | Module-linked knowledge tests; repeat observation; student learning tasks; school safety audit |
| Learning (Kirkpatrick level 2) | Self-reported by teachers | Measured by tests |

To avoid duplicate fieldwork, the two studies will share the training records extracted from Samagra Shiksha Karnataka and will not sample the same schools. The Steering Committee will review both studies together.

# 5. Alignment with national and State policy

| Document | Relevance |
| --- | --- |
| NEP 2020 | Continuous professional development of at least 50 hours a year for every teacher; teacher-led, need-based training |
| Samagra Shiksha framework and norms | In-service training, induction, and the role of SCERT and DIETs in research and evaluation |
| NISHTHA | Integrated national teacher training, delivered online through DIKSHA |
| NIPUN Bharat Mission | Foundational literacy and numeracy training for teachers of the early grades |
| NCF-SE 2023 | Competency-based pedagogy that training is expected to build |
| PARAKH Rashtriya Sarvekshan 2024 and NAS 2021 | Learning outcome data for the outcome analysis |
| National Professional Standards for Teachers (NCTE) | Reference for the expected teacher competencies |

# 6. Objectives

- To map investment in in-service teacher training from 2021-22 to 2025-26 by programme, level, fund source and district, including approvals, releases, expenditure and unit costs.

- To assess reach: the number of unique teachers trained, repeat participation, groups left out, and progress towards the NEP norm of 50 hours of professional development a year.

- To assess the quality and relevance of training, including design, the Master Resource Person (MRP) cascade, materials and timing.

- To assess the transfer of training to classroom practice.

- To examine the association between training intensity and student learning outcomes.

- To identify bottlenecks in fund flow and implementation, including trainings approved but not conducted.

- To estimate cost-effectiveness and recommend a rationalised, evidence-based teacher professional development plan for the State.

# 7. Evaluation questions

| No. | Evaluation question | Objective |
| --- | --- | --- |
| EQ1 | How much was approved, released and spent on each programme each year, and at what cost per teacher and per training day? | 1 |
| EQ2 | How many individual teachers were trained, how often, and which groups were reached least? | 2 |
| EQ3 | How do teachers and resource persons rate the relevance and quality of each programme? | 3 |
| EQ4 | Do teachers with more relevant training show stronger classroom practice than those with less? | 4 |
| EQ5 | Are districts with higher training intensity associated with better learning outcomes in PARAKH Rashtriya Sarvekshan 2024, after taking account of their NAS 2021 results? | 5 |
| EQ6 | Why were some approved trainings delayed or not conducted, and why was released money not spent? | 6 |
| EQ7 | Which programmes give the most observed change in practice per rupee? | 7 |

# 8. Evaluation framework

The study combines two established frameworks. The CIPP model (Context, Input, Process, Product) organises the evaluation of the programme as a whole. The Kirkpatrick model traces each training programme through four levels: reaction, learning, behaviour and results.

| Level | What is measured | Source |
| --- | --- | --- |
| Input (investment) | Approvals, releases, expenditure, unit costs, timeliness of funds | PAB minutes, PFMS records, progress reports |
| Process (reach) | Unique teachers trained, days of training, groups reached | Training registers, DIKSHA records, teacher database |
| Kirkpatrick 1-2 (reaction, learning) | Relevance, quality, knowledge gained (self-reported) | Teacher survey; FGDs with teachers and resource persons |
| Kirkpatrick 3 (behaviour) | Classroom practice | Observation of 816 classrooms (World Bank Teach tool) |
| Kirkpatrick 4 (results) | Student learning | NAS 2021, PARAKH 2024, State Learning Achievement Survey, SSLC |
| Product (value) | Cost per teacher, per training day and per unit of change | Combined analysis |

# 9. Scope and sample

The desk review covers every in-service teacher training programme from 2021-22 to 2025-26. The field study covers all 34 educational districts, with 12 Government schools per district drawn by stratified random sampling (by rural or urban location, and by lower primary, higher primary or high school).

| Unit | Per district | State total | Selection |
| --- | --- | --- | --- |
| Schools | 12 | 408 | Stratified random |
| Teachers surveyed | 36 (3 per school) | 1,224 | Stratified by training exposure from records |
| Classroom observations | 24 (2 per school) | 816 | Surveyed teachers, in their own classes |
| Head teachers | 12 | 408 | All sampled schools |
| Focus group discussions | 2 | 68 | One with teachers; one with MRPs, BRPs and CRPs |
| In-depth interviews | 5 | 170 | DDPI, BEO, DIET Principal, BRC Coordinator and one MRP |
| Programme case studies | - | 12 | Programmes selected for scale, cost or performance |

The inception report will include a power calculation for the teacher-level comparison (EQ4), using intra-class correlations estimated from the pilot.

# 10. Methodology

## 10.1 Component 1: Investment analysis

All PAB approvals, releases and expenditure records for 2021-22 to 2025-26 are compiled into one database. The analysis covers utilisation ratios, the time between release and training, unit costs per teacher and per training day, and the spread across fund sources (Samagra Shiksha through PFMS, EQIP and others) and districts. All percentages are recomputed from the source figures, and discrepancies are reported (Annexure II).

## 10.2 Component 2: Reach and coverage

Training registers, DIKSHA completion records and the State’s teacher database are linked to count individual teachers rather than attendances. The analysis shows repeat participation, teachers never trained, groups with low reach, and hours of training per teacher per year against the NEP norm of 50 hours.

## 10.3 Component 3: Quality and transfer to practice

- Teacher survey: training received, relevance, quality, use in class and barriers.

- Classroom observation: the World Bank Teach tool, with a short log of the practices each programme was meant to build. Teach was designed for primary classrooms; its use in high school classrooms will be tested in the pilot, and any adaptation will be documented in the inception report.

- FGDs and interviews: design and timing, the MRP cascade, materials, follow-up support, and reasons for delays.

- Case studies: 12 programmes, including NISHTHA, induction training, Marusinchana, Ganitha Ganaka, Odu Karnataka, Kalika Deepa, subject-wise training, IISc and Guruchetana.

## 10.4 Component 4: Outcomes

District-level training intensity (teacher-days per teacher) is related to learning outcomes, controlling for district characteristics. NAS 2021 assessed Classes 3, 5, 8 and 10, and PARAKH Rashtriya Sarvekshan 2024 assessed Classes 3, 6 and 9. Change over time is therefore analysed only for Class 3, the grade common to both surveys. For other grades, PARAKH 2024 results are analysed with NAS 2021 district results as a control for prior performance. State Learning Achievement Survey and SSLC results are used as further evidence. At teacher level, observed practice is compared across levels of training exposure.

## 10.5 Component 5: Cost-effectiveness and synthesis

Costs from Component 1 are combined with reach and practice results to estimate the cost per teacher reached and per unit of observed change, by programme. Findings are brought together in a joint display for each objective and validated in divisional and State workshops.

## 10.6 Analysis

- Quantitative (SPSS/R): descriptive and trend analysis; multilevel models of teachers within schools within districts; district panel models for learning outcomes; cost-effectiveness ratios.

- Qualitative: thematic analysis of FGDs, interviews and case studies, with double coding of 10 per cent of transcripts.

- Reliability: observers certified before fieldwork; double observation in 10 per cent of classrooms.

# 11. Implementation strategy and institutional arrangement

- State level (DSERT): a Principal Investigator, two Research Associates, a statistician and a finance and data assistant. A Steering Committee chaired by the Director, DSERT, meets every quarter. A Technical Advisory Committee includes experts in evaluation, teacher education, statistics and public finance.

- District level (34 DIETs): the DIET Principal is the nodal officer, one faculty member is the District Coordinator, and two trained investigators work in each district.

- Convergence: Samagra Shiksha Karnataka for PAB, release and PFMS records; the State teacher database; DIKSHA records.

# 12. Action plan

| Phase | Months | Activity | Responsibility | Deliverable |
| --- | --- | --- | --- | --- |
| 1. Preparation | M1 | Constitute committees; orient 34 DIET Principals and coordinators | DSERT | Committee orders |
|  | M1-M3 | Collect PAB, release, PFMS and training records for 2021-22 to 2025-26 | State team; Samagra Shiksha Karnataka | Raw data |
|  | M1-M3 | Develop tools; ethics clearance | State team | Tools; clearance |
|  | M3-M4 | Train coordinators and investigators; certify observers; pilot in 8 schools; power calculation | State team; DIETs | Inception report (M4) |
| 2. Investment analysis | M3-M7 | Build the reconciled database; investment and reach analysis | State team | Investment and reach report (M7) |
| 3. Field study | M5-M9 | Teacher survey, 816 observations, 68 FGDs, 170 interviews | DIETs | Field dataset |
|  | M7-M9 | 12 programme case studies | State team; DIETs | Case reports |
| 4. Outcome analysis | M9-M12 | Outcome linkage; cost-effectiveness | State team | Interim report (M12) |
|  | M11-M13 | Integrated analysis; 34 district briefs | State team | District briefs |
| 5. Synthesis | M14-M15 | Four divisional validation workshops | DSERT; DIETs | Validated findings |
|  | M16 | State validation workshop | DSERT | Agreed recommendations |
|  | M15-M18 | Final report, policy brief and evaluation dashboard | State team | Final report (M18) |
|  | M18 | Dissemination; handover of database and dashboard | DSERT | Database and dashboard |
| Throughout | M1-M18 | Quarterly Steering Committee; monitoring visits | DSERT | Minutes; monitoring reports |

# 13. Gantt chart

Milestone reports: M4 inception report; M7 investment and reach report; M12 interim report; M18 final report.

# 14. Budget

The total cost of the study is ₹96,01,200 (Rupees Ninety-Six Lakh One Thousand Two Hundred only) for 18 months: ₹76,55,550 in Year 1 (Months 1-12) and ₹19,45,650 in Months 13-18. Unit costs are indicative and will be finalised against the Samagra Shiksha norms in force at the time of approval.

Summary of budget by head (₹)

| Budget head | Year 1 | Months 13-18 | Total | Share |
| --- | --- | --- | --- | --- |
| A. Personnel | 20,52,000 | 8,76,000 | 29,28,000 | 30.5% |
| B. Field data collection | 22,44,000 | - | 22,44,000 | 23.4% |
| C. Travel and daily allowance | 9,86,000 | 85,000 | 10,71,000 | 11.2% |
| D. Training, meetings and workshops | 8,35,000 | 4,40,000 | 12,75,000 | 13.3% |
| E. Tools, technology, printing and ethics | 11,74,000 | - | 11,74,000 | 12.2% |
| F. Reporting and dissemination | - | 4,52,000 | 4,52,000 | 4.7% |
| G. Contingency and administration (5%) | 3,64,550 | 92,650 | 4,57,200 | 4.8% |
| Grand total | 76,55,550 | 19,45,650 | 96,01,200 | 100.0% |

Detailed budget (₹)

| No. | Head | Item | Unit cost and quantity | Year 1 | Months 13-18 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | A | State Research Associates | 2 × 30,000 × 18 months | 7,20,000 | 3,60,000 | 10,80,000 |
| 2 | A | Statistician / data analyst | 1 × 35,000 × 18 months | 4,20,000 | 2,10,000 | 6,30,000 |
| 3 | A | Finance and data assistant (PFMS and training-record reconciliation) | 1 × 25,000 × 12 months | 3,00,000 | - | 3,00,000 |
| 4 | A | District Coordinators (DIET faculty honorarium) | 34 × 1,500 × 18 months | 6,12,000 | 3,06,000 | 9,18,000 |
| 5 | B | Field investigator days | 408 schools × 2 × 1.5 days × 1,000 | 12,24,000 | - | 12,24,000 |
| 6 | B | District records retrieval and data entry (training registers, attendance, utilisation) | 34 × 10,000 | 3,40,000 | - | 3,40,000 |
| 7 | B | FGD facilitation and refreshments | 68 FGDs × 3,000 | 2,04,000 | - | 2,04,000 |
| 8 | B | Transcription and translation | 238 FGDs and IDIs × 2,000 | 4,76,000 | - | 4,76,000 |
| 9 | C | Investigator travel to schools | 408 schools × 1,500 | 6,12,000 | - | 6,12,000 |
| 10 | C | State team monitoring visits | 34 districts × 6,000 | 2,04,000 | - | 2,04,000 |
| 11 | C | District Coordinators to State review meetings | 34 × 3 meetings × 2,500 | 1,70,000 | 85,000 | 2,55,000 |
| 12 | D | State-level training of trainers for District Coordinators | 50 participants × 3 days × 1,500 | 2,25,000 | - | 2,25,000 |
| 13 | D | District investigator training | 34 × 15,000 | 5,10,000 | - | 5,10,000 |
| 14 | D | Steering and Technical Advisory Committee meetings | 6 × 25,000 | 1,00,000 | 50,000 | 1,50,000 |
| 15 | D | Divisional validation workshops | 4 × 60,000 | - | 2,40,000 | 2,40,000 |
| 16 | D | State validation and dissemination workshop | 1 × 1,50,000 | - | 1,50,000 | 1,50,000 |
| 17 | E | Tablets (retained by DIETs) | 34 × 15,000 | 5,10,000 | - | 5,10,000 |
| 18 | E | Mobile data allowance | 68 investigators × 500 × 6 months | 2,04,000 | - | 2,04,000 |
| 19 | E | Integrated evaluation database and dashboard | Lump sum | 1,50,000 | - | 1,50,000 |
| 20 | E | Tool development and pilot in 8 schools | Lump sum | 1,00,000 | - | 1,00,000 |
| 21 | E | Printing of tools and consent forms | Lump sum | 1,00,000 | - | 1,00,000 |
| 22 | E | Qualitative analysis software | Lump sum | 60,000 | - | 60,000 |
| 23 | E | Ethics review | Lump sum | 50,000 | - | 50,000 |
| 24 | F | Report writing, editing, design and printing | 500 copies | - | 3,00,000 | 3,00,000 |
| 25 | F | District briefs and policy brief (Kannada and English) | 34 × 3,000 + 50,000 | - | 1,52,000 | 1,52,000 |
| 26 | G | Contingency and administration | 5% of sub-total | 3,64,550 | 92,650 | 4,57,200 |
|  |  | Grand total |  | 76,55,550 | 19,45,650 | 96,01,200 |

Funding pattern (₹)

Karnataka falls under the 60:40 Centre-State sharing pattern of Samagra Shiksha.

| Period | Central share (60%) | State share (40%) | Total |
| --- | --- | --- | --- |
| Year 1 | 45,93,330 | 30,62,220 | 76,55,550 |
| Months 13-18 | 11,67,390 | 7,78,260 | 19,45,650 |
| Total | 57,60,720 | 38,40,480 | 96,01,200 |

Proposed release. Funds are sought in phases linked to milestones: the first release on approval; later releases on acceptance of the inception report (M4), the investment and reach report (M7) and the interim report (M12), together with utilisation certificates.

# 15. Monitoring and review

- Quarterly Steering Committee reviews of progress and expenditure.

- A monitoring visit by the State team to each district; back-checks of 10 per cent of field records.

- Quarterly physical and financial progress reports to Samagra Shiksha Karnataka; utilisation certificates as per scheme norms.

# 16. Ethics

- Ethics clearance before fieldwork (by Month 3).

- Informed consent from teachers, head teachers and officials.

- Observation is used for evaluation only; no individual teacher’s score is shared with supervisors or used for appraisal.

- Teacher records are pseudonymised after linkage and handled under the Digital Personal Data Protection Act, 2023.

# 17. Risks and mitigation

| Risk | Mitigation |
| --- | --- |
| Records for early years are incomplete or in different formats | Early data request through Samagra Shiksha Karnataka; district record retrieval; gaps reported openly |
| Teachers cannot be matched across training records | Matching on teacher ID where available, otherwise on name, school and date of birth; match rate reported |
| Teachers change their practice when observed | Research-only use made clear; first 10 minutes not scored |
| Outcome links mistaken for cause | Results reported as associations; triangulated with practice and case-study evidence |
| Learning surveys test different grades | Change over time analysed only for Class 3; other grades analysed with prior district results as a control |
| Overlap with the companion study | Shared training records; separate school samples; joint review by the Steering Committee |
| Delay in release of funds | Phase-wise release; 5 per cent contingency |

# 18. Expected outcomes and deliverables

- A reconciled database of investment in teacher training, 2021-22 to 2025-26, with an interactive dashboard for DSERT.

- An investment and reach report, including unit costs and groups left out.

- Evidence on the quality of each major programme and on its transfer to classroom practice.

- An analysis of training intensity and learning outcomes by district.

- A ranking of programmes by cost-effectiveness.

- A rationalised teacher professional development plan for the next phase of Samagra Shiksha, a policy brief and 34 district briefs.

Sustainability. The database and dashboard remain with DSERT and can be updated each year from PAB and PFMS records, turning this one-time evaluation into a standing monitoring system.

# 19. Limitations

The evaluation is retrospective and observational, so links between training and learning are associations, not proof of cause. Learning in Kirkpatrick level 2 is self-reported. The quality of the investment analysis depends on the completeness of records for the earlier years. Findings apply to Government schools.

# 20. Certificate

Certified that the proposed study does not duplicate any activity approved for the State under Samagra Shiksha or any other scheme of the Government of India; that it has been designed to complement, and not to repeat, the companion proposal submitted by DSERT; that the costs have been worked out as per scheme norms; and that the funds will be used only for the purpose for which they are sanctioned.

Director
Department of State Educational Research and Training
Bengaluru

# Annexure I: Programme-wise progress, 2022-23 to 2025-26

Compiled from the State’s progress records. Percentages are recomputed from the figures; “-” means not reported.

2022-23

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| English Nali-Kali Levels 1 and 2: teacher training | 1,018 | 1,014 | 99.6 | 13.46 | 11.67 | 86.7 | SSK (PFMS) |
| English Nali-Kali Levels 1 and 2: MRP training | - | - | - | 1.12 | 0.64 | 57.1 | SSK (PFMS) |
| English Nali-Kali 1 and 2: DIKSHA upload | - | - | - | 1.53 | 0.53 | 34.6 | SSK (PFMS) |
| NISHTHA 3.0 online, primary (2021-22, 2nd instalment) | 51,056 | 94,401 | 184.9 | 424.80 | 329.90 | 77.7 | SSK (PFMS) |
| NISHTHA 2.0 online, secondary (2021-22, 2nd instalment) | 58,249 | 54,165 | 93.0 | 439.34 | 387.61 | 88.2 | SSK (PFMS) |
| IISc training | 400 | 395 | 98.8 | 51.00 | 44.47 | 87.2 | EQIP |
| Guruchetana module: face-to-face training | 1,700 | 1,684 | 99.1 | 25.00 | 23.89 | 95.6 | EQIP |
| NIPUN Karnataka training | - | - | - | 159.80 | 44.28 | 27.7 | SSK (PFMS) |
| Total |  |  |  | 1,116.05 | 842.98** | 75.5 |  |

** As recorded; the rows add to 842.99 because of rounding in the source.

2023-24

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Subject-wise training, high school teachers of Classes 9-10 | 10,000 | 10,051 | 100.5 | 250.00 | 240.16 | 96.1 | SSK (PFMS) |
| IISc training | 300 | 322 | 107.3 | 40.00 | 36.94 | 92.4 | EQIP |
| Total | 10,300 | 10,373 | 100.7 | 290.00 | 277.10 | 95.6 |  |

2024-25: primary school teachers

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Marusinchana (Classes 6-7): MRP training | 340 | 321 | 94.4 | 14.00 | 9.15 | 65.4 | SSK (PFMS) |
| Induction MRP training (GPT teachers) | 136 | 136 | 100.0 | 10.40 | 7.99 | 76.8 | TBF |
| Ganitha Ganaka: MRP training | 72 | 72 | 100.0 | 2.88 | 1.50 | 52.1 | K2 |
| English Nali-Kali (Classes 1-3) | 1,195 | 1,146 | 95.9 | 21.51 | 18.18 | 84.5 | SSK |
| Induction training (GPT teachers) | 6,209 | 5,506 | 88.7 | 170.74 | 141.32 | 82.8 | TBF |
| Ganitha Ganaka: teacher training (Classes 3-5) | 34,960 | 32,770 | 93.7 | 114.00 | 78.15 | 68.6 | K2 |
| Marusinchana (Classes 6-7): teacher training | 36,520 | 31,009 | 84.9 | 328.68 | 170.99 | 52.0 | SSK (PFMS) |
| PAB-approved in-service training (Classes 6-8) | 20,767 | 19,430 | 93.6 | 519.15 | 505.35 | 97.3 | SSK (PFMS) |
| Total | 1,00,199 | 90,390 | 90.2 | 1,181.36 | 932.63 | 78.9 |  |

2024-25: high school teachers

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Marusinchana (Classes 8-10): MRP training | 344 | 333 | 96.8 | 10.20 | 9.99 | 97.9 | SSK (PFMS) |
| Marusinchana (Classes 8-10): teacher training | 10,034 | 9,169 | 91.4 | 90.30 | 82.46 | 91.3 | SSK (PFMS) |
| PAB-approved in-service training (Classes 9-10) | 9,439 | 8,168 | 86.5 | 235.89 | 227.57 | 96.5 | SSK (PFMS) |
| IISc training (science and mathematics teachers) | 300 | 293 | 97.7 | 43.30 | 38.97 | 90.0 | EQIP |
| Total | 20,117 | 17,963 | 89.3 | 379.69 | 358.99 | 94.5 |  |

2025-26 (as on 31.03.2026): primary school teachers, component F.01.17.01

| Programme (days) | Phys. target | Achieved | % | Fin. target, 1st instalment (₹ lakh) | Released (₹ lakh) | Spent (₹ lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Induction (ICT) and Kalika Deepa (5) | 5,000 | 4,823 | 96.5 | 95.00 | 47.50 | 43.17 |
| POCSO awareness, eradication of corporal punishment, Marusinchana (science and mathematics), Jnana Setu, value education (5) | 51,781 | 42,415 | 81.9 | 491.92 | 457.90 | 363.05 |
| Adivasi residential school teachers (3) | 592 | 155 | 26.2 | 3.37 | 3.37 | 0.41 |
| State-level MRP training: Marusinchana, Jnana Setu, Ganitha Ganaka, Odu Karnataka, Kalika Deepa (5) | 4,511 | 3,864 | 85.7 | 155.63 | 155.63 | 47.55 |
| State-level Nali-Kali MRP training (2) | 1,984 | - | - | 27.38 | - | 0.00 |
| MRP training: POCSO, corporal punishment, value education (3) | 1,984 | 1,902 | 95.9 | 41.07 | 10.51 | 10.99 |
| Training of educational administrators | 1,000 | - | - | 30.00 | - | 0.00 |
| Ganitha Kalika Andolana | 25,891 | 0 | 0.0 | - | - | - |
| Total |  |  |  | 844.37 | 674.91 | 465.17 |

2025-26 (as on 31.03.2026): high school teachers, component F.03.11.01

| Programme (days) | Phys. target | Achieved | % | Fin. target, 1st instalment (₹ lakh) | Released (₹ lakh) | Spent (₹ lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Induction-1, induction refresher and Kalika Deepa (5) | 3,000 | 2,678 | 89.3 | 57.00 | 28.50 | 24.12 |
| Eradication of corporal punishment, POCSO, career counselling awareness, value education, Marusinchana, Jnana Setu (6) | 44,218 | 18,491 | 41.8 | 504.09 | 470.29 | 168.50 |
| BRP/ECO and other trainings for high school teachers (10) | 1,420 | - | - | 26.98 | - | 0.00 |
| Content enrichment, Government school teachers | 44,218 | - | - | - | - | 0.00 |
| Content enrichment, aided school teachers | 23,461 | - | - | - | - | 0.00 |
| Total |  |  |  | 588.07 | 498.79 | 192.62 |

2025-26 (as on 31.03.2026): component F.01.22.02

| Programme (days) | Phys. target | Achieved | % | Fin. target, 1st instalment (₹ lakh) | Released (₹ lakh) | Spent (₹ lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Induction training (elementary) | 12,600 | 11,515 | 91.4 | 315.00 | 119.70 | 92.59 |
| Odu Karnataka (1), Ganitha Ganaka (½) and value education (½) | 51,919 | 49,584 | 95.5 | 519.19 | 197.29 | 178.00 |
| Odu Karnataka (1) | 23,010 | - | - | 259.60 | - | 0.00 |
| Total |  |  |  | 1,093.79 | 316.99 | 270.59 |
| Grand total, 2025-26 |  |  |  | 2,526.23 | 1,490.69 | 928.38 |

SSK: Samagra Shiksha Karnataka; PFMS: Public Financial Management System; EQIP: grant as recorded in the source; K2 and TBF: fund codes as recorded in the source, to be mapped to scheme heads in Component 1.

# Annexure II: Data discrepancies found in the progress records

| No. | Record | Discrepancy | Action in this study |
| --- | --- | --- | --- |
| 1 | 2023-24, subject-wise training, Classes 9-10 | Physical achievement reported as 110.65%; the figures (10,051 of 10,000) give 100.51% | Recompute all percentages from source figures |
| 2 | 2023-24, IISc training | Financial achievement reported as 87.20% (the same as in 2022-23); the figures (₹36.94 lakh of ₹40.00 lakh) give 92.35% | Verify against PFMS |
| 3 | 2022-23, NISHTHA 3.0 (primary) | 94,401 trained against a target of 51,056 (184.9%) | Count unique teachers from DIKSHA records |
| 4 | 2025-26, MRP training on POCSO, corporal punishment and value education | Expenditure (₹10.99 lakh) exceeds funds released (₹10.51 lakh) | Reconcile release and expenditure |
| 5 | 2025-26, high school induction | Recorded as “9 days + 1 day (total 5 days)” | Confirm the actual duration |
| 6 | 2023-24, all programmes | Only two programmes are reported for the year | Obtain the full PAB-approved list |

# Annexure III: References

- Kirkpatrick, D. L. and Kirkpatrick, J. D. (2006). Evaluating Training Programs: The Four Levels (3rd ed.). San Francisco: Berrett-Koehler.

- Stufflebeam, D. L. and Zhang, G. (2017). The CIPP Evaluation Model: How to Evaluate for Improvement and Accountability. New York: Guilford Press.

- World Bank. Teach: Classroom Observation Tool. Washington, DC: World Bank.

- Ministry of Education (2020). National Education Policy 2020. Government of India.

- Ministry of Education. Samagra Shiksha: Framework for Implementation. Government of India.

- NCERT. National Achievement Survey 2021; PARAKH Rashtriya Sarvekshan 2024. New Delhi: NCERT.

- NCERT (2023). National Curriculum Framework for School Education 2023. New Delhi: NCERT.

- NCTE. National Professional Standards for Teachers. New Delhi: NCTE.

- Government of India. Digital Personal Data Protection Act, 2023.