# PROPOSAL FOR APPROVAL UNDER SAMAGRA SHIKSHA

Government of Karnataka

Investment to Impact: An Integrated Evaluation of In-service Teacher Training in Karnataka, 2022-23 to 2025-26

| Name of the State | Karnataka |
| --- | --- |
| Title of the proposal | Investment to Impact: An Integrated Evaluation of In-service Teacher Training in Karnataka, 2022-23 to 2025-26 |
| Scheme and component | Samagra Shiksha: Teacher Education (research and evaluation by SCERT and DIETs) |
| Implementing agency | Department of State Educational Research and Training (DSERT), Karnataka, with the 34 District Institutes of Education and Training (DIETs) |
| Nodal officer | Senior Assistant Director (Teacher Education and Research), DSERT, Bengaluru |
| Period evaluated | 2022-23 to 2025-26 (four years) |
| Duration of the study | 18 months (Month 1 to Month 18) |
| Coverage | Desk review of all in-service teacher training programmes under Samagra Shiksha and allied grants; field study in 612 Government schools across the 34 DIET districts: up to 2,448 teachers (about 2,450), 612 classrooms observed, about 9,180 students; a prospective cohort of 204 newly trained teachers |
| Total cost | ₹1,47,75,600 (Year 1: ₹1,21,26,400; Months 13-18: ₹26,49,200) |
| Central share (60%) / State share (40%) | ₹88,65,360 / ₹59,10,240 |

# Abbreviations

| Abbreviation | Expansion |
| --- | --- |
| APF | Azim Premji Foundation |
| BEO | Block Education Officer |
| BRC | Block Resource Centre |
| BRP | Block Resource Person |
| CIPP | Context, Input, Process, Product (evaluation model) |
| CPD | Continuous professional development |
| CRP | Cluster Resource Person |
| DDPI | Deputy Director of Public Instruction |
| DIET | District Institute of Education and Training |
| DIKSHA | Digital Infrastructure for Knowledge Sharing |
| DSERT | Department of State Educational Research and Training |
| ECO | Education Coordinator |
| EMTIP | English Medium Teachers Induction Programme |
| FGD | Focus group discussion |
| GPT | Graduate Primary Teacher |
| ICT | Information and Communication Technology |
| IDI | In-depth interview |
| IISc | Indian Institute of Science |
| MIS | Management Information System |
| MRP | Master Resource Person |
| NAS | National Achievement Survey |
| NCF-SE | National Curriculum Framework for School Education |
| NCTE | National Council for Teacher Education |
| NEP | National Education Policy |
| NIPUN | National Initiative for Proficiency in Reading with Understanding and Numeracy |
| NISHTHA | National Initiative for School Heads’ and Teachers’ Holistic Advancement |
| PAB | Project Approval Board |
| PARAKH | Performance Assessment, Review and Analysis of Knowledge for Holistic Development |
| PFMS | Public Financial Management System |
| POCSO | Protection of Children from Sexual Offences |
| RTE | Right of Children to Free and Compulsory Education |
| SCERT | State Council of Educational Research and Training |
| SSK | Samagra Shiksha Karnataka |
| TALP | Technology Assisted Learning Programme |
| UDISE+ | Unified District Information System for Education Plus |

EQIP, K2 and TBF are fund codes as recorded in the State’s progress records; they will be mapped to scheme heads in Component 1.

# Summary

Between 2022-23 and 2025-26 the State’s progress records show a combined financial target of ₹5,493 lakh for in-service teacher training and recorded expenditure of ₹3,340 lakh (61 per cent). The records count teachers trained and money spent. They do not show whether training reached the teachers who needed it, whether teachers learned from it and used it, whether schools supported them, whether students gained, or why several approved trainings were never held.

This study answers these questions in one design, at two levels. At system level it builds a reconciled database of every programme, counts unique teachers reached and traces bottlenecks in fund flow. At classroom level it follows four clusters of training (subject packages; child protection, safety and awareness; ICT; and partnership trainings) from the training hall into 612 classrooms in all 34 DIET districts. It uses Guskey’s five levels of professional development evaluation, tests teachers and about 9,180 students, and follows a new cohort of 204 teachers before and after training to test whether change lasts. It estimates the cost per teacher reached and per unit of practice change, and leaves DSERT a Karnataka Teacher Professional Development Framework, validated tools and a dashboard that can be updated every year. The cost is ₹1.48 crore over 18 months, shared 60:40 between the Centre and the State.

# 1. Background

Between 2022-23 and 2025-26 Karnataka has run a large programme of in-service teacher training under Samagra Shiksha, supported by allied grants. It includes NISHTHA online courses; induction training for newly recruited teachers; subject-wise training for high school teachers; foundational literacy and numeracy programmes (Odu Karnataka, Ganitha Ganaka, Kalika Deepa, English Nali-Kali); the Marusinchana and Jnana Setu programmes; training with the Indian Institute of Science (IISc); the Guruchetana module; ICT training through TALP and the Digital Library; partnership training with the Azim Premji Foundation (APF); training for teachers of bilingual schools (EMTIP); and orientation on child protection (POCSO), eradication of corporal punishment, child rights, road safety, value education and career counselling.

These programmes are monitored through physical and financial progress reports: how many teachers were trained against the target, and how much was spent against the allocation. The reports do not show whether training changed what teachers do in classrooms, whether schools helped them to apply it, or whether students learned more as a result. After four years of investment, and as the State prepares its plans for the next phase of Samagra Shiksha, an integrated evaluation is due.

# 2. What the progress records show

The State’s progress records for 2022-23 to 2025-26 report a combined financial target of ₹5,493 lakh for in-service teacher training, against recorded expenditure of ₹3,340 lakh (61 per cent). For 2025-26 the target shown is the first instalment only, as on 31.03.2026. Programme-wise details are at Annexure I.

| Year | Teachers targeted | Teachers trained | Financial target (₹ lakh) | Expenditure (₹ lakh) | Expenditure as % of target |
| --- | --- | --- | --- | --- | --- |
| 2022-23 | 1,12,423* | 1,51,659* | 1,116.05 | 842.98 | 75.5% |
| 2023-24 (two programmes reported) | 10,300 | 10,373 | 290.00 | 277.10 | 95.6% |
| 2024-25 | 1,20,316 | 1,08,353 (90.1%) | 1,561.05 | 1,291.62 | 82.7% |
| 2025-26 (as on 31.03.2026; first instalment) | See Annexure I | See Annexure I | 2,526.23 | 928.38 | 36.7% |
| Total, 2022-23 to 2025-26 |  |  | 5,493.33 | 3,340.08 | 60.8% |

* 2022-23 includes NISHTHA online course completions, which exceed the target (184.9 per cent for primary teachers) and may count course enrolments rather than individual teachers.

Patterns that call for evaluation

- Falling utilisation. Expenditure in 2025-26 was 37 per cent of the first-instalment target and 62 per cent of the funds released to districts (₹928.38 lakh spent of ₹1,490.69 lakh released).

- Approved trainings not started. By 31.03.2026 no expenditure was recorded for content enrichment training (67,679 Government and aided school teachers targeted), Ganitha Kalika Andolana (25,891 teachers), Odu Karnataka one-day training (23,010 teachers), State-level Nali-Kali MRP training, BRP/ECO training, or training of educational administrators.

- Groups with low reach. Adivasi residential school teachers (155 of 592, 26 per cent) and high school teachers in the six-day 2025-26 package (18,491 of 44,218, 42 per cent).

- Low spending on some programmes. NIPUN Karnataka training in 2022-23 (28 per cent of the allocation) and Marusinchana for Classes 6-7 in 2024-25 (52 per cent).

- Strong performers. Subject-wise training for Classes 9-10 in 2023-24 (96 per cent of funds used), PAB-approved in-service training for Classes 6-8 in 2024-25 (97 per cent), and the Odu Karnataka-Ganitha Ganaka package in 2025-26 (96 per cent of teachers reached).

- Data quality. Several reported percentages do not match the underlying figures, one programme records spending above the funds released, and only two programmes are reported for 2023-24 (Annexure II).

# 3. Rationale and need

The State needs to know which of its teacher training investments change classroom practice and learning, at what cost, and why some programmes do not reach their targets. Progress reports answer only the first link in that chain.

| Question the State needs answered | What is available now | What this evaluation adds |
| --- | --- | --- |
| How much was invested, where and on what? | Year-wise physical and financial reports, in different formats | One reconciled database, 2022-23 to 2025-26, by programme, level, fund source and district |
| Who was reached, and who was missed? | Counts of participants against targets | Unique teachers reached, repeat training, groups left out, and progress towards 50 hours of CPD a year |
| Was the training good, and did teachers learn? | Pre- and post-tests for some trainings, not compiled | Observation of live sessions; module-linked knowledge tests; loss of content along the cascade |
| Did schools help teachers apply it? | Not assessed | Head teacher, CRP and BRP support; materials, devices and time in the timetable |
| Did classroom practice change, and does it last? | Not assessed | Observation of 612 classrooms with one common tool; before-and-after observation of a new cohort |
| Did students gain? | NAS, PARAKH and SSLC results, not linked to training | Learning tasks for students of observed teachers; safety awareness; district-level linkage |
| Was it value for money? | Not assessed | Cost per teacher reached and per unit of practice change, by cluster and delivery model |

Two further needs shape the design. First, the departmental cascade (State to Master Resource Person to teacher) and the APF model of direct, sustained engagement have run side by side; their relative effect and cost are not known. Second, different kinds of training call for different evidence: subject training should change teaching and learning, while awareness training should change knowledge, procedures and school safety. The study judges each cluster against its own purpose.

# 4. Design in brief: one study, two levels

|  | System level | Classroom level |
| --- | --- | --- |
| Main question | Was the State’s training investment well planned, funded, delivered and spread? | Does each cluster of training change practice and learning, and why? |
| Unit of analysis | Programme, fund source and district | Teacher, classroom and student |
| Components | 1. Investment, reach and bottlenecks | 2. Training quality and learning; 3. School support and classroom practice; 4. Student outcomes |
| Shared | Component 5: cost-effectiveness and synthesis; one set of records, one sample, one team, one Steering Committee |  |

Because both levels draw on the same records and the same 34 DIET districts, findings at one level explain those at the other. Low reach or unspent funds recorded in Component 1, for example, can be checked against the support and practice observed in schools in Components 3 and 4.

# 5. Evidence from earlier studies and the gap

International reviews find that professional development changes teaching and learning when it focuses on specific subject content, gives teachers active practice of new methods, and is sustained and followed up in the classroom (Desimone, 2009; Darling-Hammond, Hyler and Gardner, 2017). Coaching shows large effects on instruction and smaller effects on achievement, and effects are smaller in larger programmes (Kraft, Blazar and Hogan, 2018). A review of programmes in low- and middle-income countries found that the features linked to larger learning gains, such as subject focus, lesson practice and follow-up visits, were less common in government programmes delivered at scale (Popova et al., 2022). Kennedy (2016) shows that programmes which prescribe practices without helping teachers adapt them have weaker effects, and evidence from India shows that results depend on how programmes are delivered through government systems (Banerjee et al., 2017).

In Karnataka, monitoring of in-service training records participation and expenditure. There is no State-level evidence on (a) how many individual teachers are reached and how often; (b) whether what is learned in training is used in classrooms and supported by schools; (c) whether the departmental cascade and direct models differ in effect and cost; and (d) what each rupee buys in changed practice. This study addresses these four gaps.

# 6. Alignment with national and State policy

| Document | Relevance |
| --- | --- |
| NEP 2020 | Continuous professional development of at least 50 hours a year for every teacher; need-based, teacher-led training |
| Samagra Shiksha framework and norms | In-service training, induction, ICT, and the role of SCERT and DIETs in research and evaluation |
| NISHTHA | Integrated national teacher training, delivered online through DIKSHA |
| NIPUN Bharat Mission | Foundational literacy and numeracy training for teachers of the early grades |
| NCF-SE 2023 | Competency-based pedagogy that training is expected to build |
| National Professional Standards for Teachers (NCTE) | Reference for the expected teacher competencies |
| POCSO Act, 2012 and RTE Act, 2009 | Duties of schools on child protection, and the prohibition of corporal punishment |
| NAS 2021 and PARAKH Rashtriya Sarvekshan 2024 | Learning outcome data for the district-level analysis |

# 7. Objectives

- To map investment in in-service teacher training from 2022-23 to 2025-26 by programme, level, fund source and district, and to identify bottlenecks in fund flow and implementation, including trainings approved but not conducted.

- To assess reach: the number of unique teachers trained, repeat participation, groups left out, and progress towards the NEP norm of 50 hours of professional development a year.

- To assess teachers’ reaction to, and learning from, each cluster of training, including the quality of the Master Resource Person (MRP) cascade.

- To assess the support that schools give teachers to apply their training, and the resulting change in classroom practice, including whether the change lasts.

- To examine the association between training and student learning, awareness and safety, at classroom and district level.

- To estimate cost-effectiveness by cluster and delivery model, and to develop a Karnataka Teacher Professional Development Framework with recommendations on training load, sequence, mode and follow-up.

# 8. Evaluation questions

| No. | Evaluation question | Objective | Component |
| --- | --- | --- | --- |
| EQ1 | How much was approved, released and spent on each programme each year, at what cost per teacher and per training day, and why were some approved trainings delayed or not conducted? | 1 | 1 |
| EQ2 | How many individual teachers were trained, how often and for how many hours, and which groups were reached least? | 2 | 1 |
| EQ3 | How do teachers rate each cluster, how much did they learn on module-linked tests, and how much content is lost along the cascade? | 3 | 2 |
| EQ4 | Do trained teachers use the practices taught, and does support from head teachers, CRPs, BRPs and school resources explain who does and who does not? | 4 | 3 |
| EQ5 | In a new cohort of trained teachers, does practice change and does it last about three months after training? | 4 | 3 |
| EQ6 | Do students of teachers with stronger practice score higher on learning tasks, and do students in trained schools know how to stay safe? Are districts with higher training intensity (2022-23 to November 2024) associated with better PARAKH 2024 results, after taking account of NAS 2021? | 5 | 4 |
| EQ7 | Does the APF direct model produce greater practice change than the departmental cascade, and at what cost? | 4, 6 | 3, 5 |
| EQ8 | What is the cost per teacher reached and per unit of practice change, by cluster and delivery model? | 6 | 5 |

Main and exploratory comparisons. The sample is sized for two main comparisons: (i) the departmental cascade against the APF direct model (EQ7); and (ii) dose-response, relating hours and number of trainings to observed practice (EQ4). Comparisons by delivery mode (face-to-face, blended, online) and between package and standalone training are reported as exploratory.

# 9. Evaluation framework

The study combines two established frameworks. The CIPP model (Context, Input, Process, Product) organises the evaluation of the programme as a whole. Guskey’s five levels of professional development evaluation trace each cluster of training from the training hall to students. Guskey’s model suits teacher training because it includes a level for organisational support: whether the school helps teachers apply what they learned.

| Stage | What is measured | Main source | Comp. |
| --- | --- | --- | --- |
| Context (CIPP) | District and teacher profile; training needs; policy priorities | UDISE+, State teacher database, PAB minutes | 1 |
| Input (CIPP) | Approvals, releases, expenditure, unit costs, timeliness of funds | PAB minutes, PFMS records, progress reports | 1 |
| Process (CIPP) | Unique teachers reached, days of training, groups reached, delivery and cascade | Training registers, DIKSHA, teacher database, live-session observation | 1, 2 |
| Guskey 1: Reaction | Relevance and quality of training | Teacher survey; training-quality checklist; resource-person feedback | 2 |
| Guskey 2: Learning | Knowledge and skills gained | Module-linked tests; pre- and post-test scores in training records | 2 |
| Guskey 3: Organisational support | Help from head teachers, CRPs, BRPs; materials, devices, time | Head teacher and CRP/BRP questionnaire; school resources checklist | 3 |
| Guskey 4: Use | Change in classroom practice, and whether it lasts | Common observation tool; prospective cohort; school safety audit | 3 |
| Guskey 5: Student outcomes | Learning, attendance, safety awareness | Student learning tasks; attendance records; NAS 2021, PARAKH 2024, State assessments | 4 |
| Product (CIPP) | Cost per teacher reached and per unit of practice change | Combined analysis | 5 |

Indicators by level and cluster

| Level | A. Subject packages | B. Child protection, safety and awareness | C. ICT | D. Partnership |
| --- | --- | --- | --- | --- |
| Reaction | Relevance to syllabus and grade | Clarity of procedures | Hands-on time on devices | Depth and follow-up |
| Learning | Module test on strategies | Test on POCSO reporting, child rights and road safety rules | TALP skills test | Test on APF or bilingual teaching strategies |
| Support | Materials, CRP visits, time in the timetable | Head teacher action; committee in place | Working devices, power, connectivity | Mentor and peer support |
| Use | Package strategies seen in class | Safety measures and displays; referral procedure known | ICT and Digital Library used in lessons | Quality of practice; language use in class |
| Student outcomes | Grade 3, 5 and 8 learning tasks | Students’ awareness of safety and of whom to tell | Students’ use of digital content | Learning; bilingual proficiency |

# 10. Scope: programmes and clusters

The desk review (Component 1) covers every in-service teacher training programme from 2022-23 to 2025-26. For the field study (Components 2 to 4), programmes are grouped into four clusters. The full inventory, with the source of each figure, is at Annexure III.

| Cluster | Trainings covered | Evidence of use expected |
| --- | --- | --- |
| A. Subject and learning-programme packages | Odu Karnataka, Ganitha Ganaka, Kalika Deepa, English Nali-Kali, Marusinchana, Jnana Setu, subject-wise and PAB-approved in-service training, induction training, NISHTHA, IISc, Guruchetana | Specific teaching strategies in class; student learning in Grades 3, 5 and 8 |
| B. Child protection, safety and awareness | POCSO, eradication of corporal punishment, child rights, road safety, value education, career counselling | Teachers’ knowledge of procedures; safety measures in the school; students’ awareness |
| C. ICT | TALP induction and refresher, Digital Library training, ICT component of induction | Use of ICT and digital content in teaching; working facilities; usage records |
| D. Partnership and special trainings | Training with Azim Premji Foundation (APF); teachers of bilingual schools (EMTIP) | Depth of practice change; language use and learning in bilingual classes |

Content enrichment training and Ganitha Kalika Andolana were approved but had not started by 31.03.2026 (Annexure I). They are covered in the bottleneck analysis in Component 1, and will enter the field study only if they are conducted before the teacher sample is drawn. Training of educational administrators is covered in Component 1 only.

# 11. Sample

All 34 DIET districts are covered, with 18 Government schools per district drawn by stratified random sampling by rural or urban location and by school level (lower primary, higher primary, high school). In each school, teachers are selected from the training MIS by stratified random sampling on training exposure, so that each cluster, the APF and EMTIP groups and teachers with little or no training are adequately represented.

| Unit | Per district | State total | Selection |
| --- | --- | --- | --- |
| Schools | 18 | 612 | Stratified random |
| Teachers surveyed and tested | About 72 | About 2,450 | Up to 4 per school (all teachers in smaller schools), stratified by training exposure |
| Classrooms observed | 18 | 612 | One teacher per school, teaching Grade 3, 5 or 8 |
| Students assessed | About 270 | About 9,180 | About 15 per observed class |
| Head teachers | 18 | 612 | All sampled schools |
| CRPs and BRPs | About 7 | About 238 | All serving the sampled schools |
| Prospective cohort | 6 | 204 | Teachers attending a major training during the study; observed and tested before and about three months after |
| Live training sessions observed | 2 | 68 | Trainings running during fieldwork |
| Focus group discussions | 2 | 68 | One with teachers; one with MRPs, BRPs and CRPs |
| In-depth interviews | 5 | 170, plus 10 with APF and EMTIP staff | DDPI, BEO, DIET Principal, BRC Coordinator, one MRP |
| Case studies | - | 16 | A strong and a weak case for two settings in each cluster |

Sample size and power. If the sample is split into two equal groups, the design can detect a difference of about 0.30 standard deviations in observed classroom practice (306 classrooms in each group) and about 0.25 standard deviations in teacher knowledge scores. The dose-response analysis uses the whole sample. The size of the cascade-APF comparison depends on how many sampled teachers were trained with APF; this will be confirmed from APF records at inception, and if the group is small the comparison will be reported as exploratory. These figures assume an intra-class correlation of 0.05 at district level and 0.15 at school level, 5 per cent significance and 80 per cent power. They will be revised in the inception report using intra-class correlations estimated from the pilot, and strata sizes will be adjusted within the approved budget if needed.

Sampling rules. The observed teacher in each school is drawn from those teaching Grade 3, 5 or 8, so that student tasks can be linked to observed practice. APF and EMTIP strata are drawn only in the districts where those programmes ran; elsewhere the places are reallocated to Clusters A to C. Where a sampled school has too few eligible teachers, a replacement school is drawn from the same stratum, and all replacements are recorded. Because every district has the same number of schools, sampling weights are applied for State-level estimates. The prospective cohort is drawn from the State training calendar for the study year, outside the sampled schools.

Timing. Fieldwork is scheduled within the working months of the academic year, avoiding vacations and the examination period. Month numbers in the action plan will be fixed against the actual start date in the inception report.

# 12. Methodology

## 12.1 Approach

The study uses mixed methods with five strands: a desk analysis of financial and training records; a tracer study that follows trained teachers from training records into their schools and classrooms; a quasi-experimental comparison of teachers with different training exposure; a prospective cohort observed before and after training; and case studies of strong and weak cases.

## 12.2 Component 1: Investment, reach and bottlenecks

All PAB approvals, releases and expenditure records for 2022-23 to 2025-26 are compiled into one database, with the full PAB-approved list obtained for 2023-24. The analysis covers utilisation ratios, the time between release and training, unit costs per teacher and per training day, and the spread across fund sources (Samagra Shiksha through PFMS, EQIP and others) and districts. All percentages are recomputed from the source figures and discrepancies are reported (Annexure II). Training registers, DIKSHA completion records and the State teacher database are linked to count individual teachers rather than attendances, showing repeat participation, teachers never trained, groups with low reach, and hours of training per teacher per year against the NEP norm of 50 hours. Interviews with district and State officers explain why approved trainings were delayed or not held.

## 12.3 Component 2: Training quality and learning

Sixty-eight live training sessions are observed with a training-quality checklist, and resource persons complete a feedback form. Teachers take a short knowledge test linked to the modules they attended. Pre- and post-test scores already held in training records are compiled where available. Loss of content along the cascade is estimated by comparing session checklists and test results at State resource person, MRP and teacher level.

## 12.4 Component 3: School support and classroom practice

- One common observation tool for all 612 classrooms: the core of the World Bank Teach tool, with cluster-specific indicators drawn from the module-practice map. Teach was designed for primary classrooms; its use in high school classrooms will be tested in the pilot, and any adaptation will be documented in the inception report.

- Head teacher and CRP/BRP questionnaire and a school resources checklist for Guskey level 3.

- School safety audit for POCSO and road safety measures (Cluster B).

- Prospective cohort. 204 teachers attending a major training during the study are observed and tested before training and about three months after. This is the only valid test of whether change lasts, because most training in the evaluation period took place one to four years before fieldwork.

## 12.5 Component 4: Student outcomes

About 15 students in each observed class take short learning tasks in Kannada, English and Mathematics for Grades 3, 5 and 8, and answer general, age-appropriate questions on safety. Attendance records are compiled. At district level, training intensity (teacher-days per teacher) is related to learning outcomes, controlling for district characteristics. Only training held between 2022-23 and November 2024 is counted, because later training could not have influenced PARAKH Rashtriya Sarvekshan 2024. NAS 2021 assessed Classes 3, 5, 8 and 10, and PARAKH 2024 assessed Classes 3, 6 and 9, so change over time is analysed only for Class 3; for other grades, PARAKH 2024 results are analysed with NAS 2021 district results as a control. With 34 districts, this analysis is treated as descriptive and exploratory.

## 12.6 Component 5: Cost-effectiveness and synthesis

Costs from Component 1 and cost sheets for sampled trainings (resource persons, venue, travel, materials and teacher time) are combined with reach and practice results to estimate cost per teacher reached and cost per teacher per 0.1 standard deviation of practice change, by cluster and delivery model. Because teachers attend overlapping trainings, cost-effectiveness is estimated for clusters and delivery models, not for individual programmes. Findings are brought together in a joint display for each objective and validated in divisional and State workshops.

## 12.7 Analysis

- Quantitative (SPSS/R): descriptive and trend analysis by Guskey level, cluster, district and delivery mode; multilevel models of students within classrooms within schools within districts; propensity score matching of trained and less-trained teachers; dose-response analysis; pre-post change in the prospective cohort; district models for learning outcomes; cost-effectiveness ratios.

- Qualitative: thematic analysis of FGDs, interviews and case studies by Guskey level, with double coding of 10 per cent of transcripts.

- Reliability: observers certified before fieldwork; double observation in 10 per cent of classrooms; back-checks of 10 per cent of records.

## 12.8 The main challenge: overlapping trainings

Many teachers attended several trainings in the same period, so the effect of a single training cannot be fully separated. The design deals with this in three ways: it compares teachers who received different combinations and amounts of training; it uses a module-practice map that links each observation indicator to the module that taught it; and it uses the prospective cohort, where the training of interest is known and recent.

# 13. Implementation strategy and institutional arrangement

- State level (DSERT): the Senior Assistant Director (Teacher Education and Research) as Principal Investigator, in an ex officio capacity with no salary charged to the study; three Research Associates; a statistician; and a finance and data assistant. A Steering Committee chaired by the Director, DSERT, meets every quarter. A Technical Advisory Committee includes experts in evaluation, teacher education, assessment, statistics and public finance, and a representative of APF.

- District level (34 DIETs): the DIET Principal is the nodal officer, one faculty member is the District Coordinator, and two certified investigators work in each district. DIET faculty prepare the district training-impact profiles, which builds their capacity for evaluation research.

- Convergence: Samagra Shiksha Karnataka for PAB, release, PFMS and training MIS records; the State teacher database; DIKSHA records; the TALP programme for ICT data; APF and the EMTIP programme for partnership data, under data-sharing agreements.

# 14. Action plan

| Phase | Months | Activity | Responsibility | Deliverable |
| --- | --- | --- | --- | --- |
| 1. Preparation | M1 | Constitute committees; orient 34 DIET Principals and coordinators | DSERT | Committee orders |
|  | M1-M3 | Collect PAB, release, PFMS, training MIS, DIKSHA and TALP records | State team; Samagra Shiksha Karnataka | Raw data |
|  | M1-M3 | Develop tools and the module-practice map; ethics clearance; data-sharing agreements | State team; subject experts | Tools; clearance |
|  | M3-M4 | Train coordinators and investigators; certify observers; pilot in 10 schools; power calculation | State team; DIETs | Inception report (M4) |
| 2. Investment and reach | M3-M7 | Build the reconciled database; investment, reach and bottleneck analysis | State team | Investment and reach report (M7) |
| 3. Fieldwork | M5-M9 | Teacher survey and tests; 612 observations; student tasks; head teacher and CRP/BRP questionnaires; safety audit | DIETs | Field dataset |
|  | M5-M10 | 68 live sessions; 68 FGDs; 180 interviews | DIETs; State team | Qualitative dataset |
|  | M5-M11 | Prospective cohort: observation and tests before and after training | DIETs | Cohort dataset |
|  | M9-M11 | 16 case studies | State team; DIETs | Fieldwork report (M11); case reports |
| 4. Analysis | M10-M14 | Analysis by Guskey level and cluster; outcome linkage; cost-effectiveness | State team; statistician | Analysis tables |
|  | M14-M15 | 34 district training-impact profiles | DIETs | District profiles |
| 5. Synthesis | M15-M16 | Four divisional workshops and one State validation workshop | DSERT; DIETs | Agreed recommendations |
|  | M16-M18 | Final report, Framework, policy brief; handover of database and dashboard | State team | Final report (M18) |
| Throughout | M1-M18 | Quarterly Steering Committee; monitoring visits | DSERT | Minutes; monitoring reports |

# 15. Gantt chart

Milestone reports: M4 inception report; M7 investment and reach report; M11 fieldwork report; M18 final report.

# 16. Budget

The total cost of the study is ₹1,47,75,600 (Rupees One Crore Forty-Seven Lakh Seventy-Five Thousand Six Hundred only) for 18 months: ₹1,21,26,400 in Year 1 (Months 1-12) and ₹26,49,200 in Months 13-18. Unit costs are indicative and will be finalised against the Samagra Shiksha norms in force at the time of approval.

Summary of budget by head (₹)

| Budget head | Year 1 | Months 13-18 | Total | Share |
| --- | --- | --- | --- | --- |
| A. Personnel | 24,12,000 | 11,31,000 | 35,43,000 | 24.0% |
| B. Field data collection | 44,92,900 | - | 44,92,900 | 30.4% |
| C. Travel and daily allowance | 18,02,000 | 85,000 | 18,87,000 | 12.8% |
| D. Training, meetings and workshops | 9,10,000 | 8,05,000 | 17,15,000 | 11.6% |
| E. Tools, technology, printing and ethics | 19,32,000 | - | 19,32,000 | 13.1% |
| F. Reporting and dissemination | - | 5,02,000 | 5,02,000 | 3.4% |
| G. Contingency and administration (5%) | 5,77,500 | 1,26,200 | 7,03,700 | 4.8% |
| Grand total | 1,21,26,400 | 26,49,200 | 1,47,75,600 | 100.0% |

Detailed budget (₹)

| No. | Head | Item | Unit cost and quantity | Year 1 | Months 13-18 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | A | State Research Associates | 3 × 30,000 × 18 months | 10,80,000 | 5,40,000 | 16,20,000 |
| 2 | A | Statistician / data analyst | 1 × 35,000 × 18 months | 4,20,000 | 2,10,000 | 6,30,000 |
| 3 | A | Finance and data assistant (PFMS, training MIS and record reconciliation) | 1 × 25,000 × 15 months | 3,00,000 | 75,000 | 3,75,000 |
| 4 | A | District Coordinators (DIET faculty honorarium) | 34 × 1,500 × 18 months | 6,12,000 | 3,06,000 | 9,18,000 |
| 5 | B | Investigator days, main fieldwork | 612 schools × 2 investigators × 2 days × 1,000 | 24,48,000 | - | 24,48,000 |
| 6 | B | Prospective cohort: observation before and after training | 204 teachers × 2 rounds × 1,000 | 4,08,000 | - | 4,08,000 |
| 7 | B | Observation of live training sessions | 68 sessions × 2,000 | 1,36,000 | - | 1,36,000 |
| 8 | B | District records retrieval and data entry (registers, attendance, utilisation) | 34 × 10,000 | 3,40,000 | - | 3,40,000 |
| 9 | B | Teacher knowledge tests: printing and scoring | 2,856 tests (2,448 sample teachers; 204 cohort teachers tested twice) × 25 | 71,400 | - | 71,400 |
| 10 | B | Student learning tasks (Grades 3, 5, 8): printing and scoring | 9,180 students × 25 | 2,29,500 | - | 2,29,500 |
| 11 | B | FGD facilitation and refreshments | 68 FGDs × 3,000 | 2,04,000 | - | 2,04,000 |
| 12 | B | Transcription and translation | 248 FGDs and IDIs × 2,000 | 4,96,000 | - | 4,96,000 |
| 13 | B | Case studies of strong and weak cases | 16 × 10,000 | 1,60,000 | - | 1,60,000 |
| 14 | C | Investigator travel, main fieldwork | 612 schools × 1,500 | 9,18,000 | - | 9,18,000 |
| 15 | C | Investigator travel, prospective cohort | 204 teachers × 2 rounds × 750 | 3,06,000 | - | 3,06,000 |
| 16 | C | State team monitoring visits | 34 districts × 2 visits × 6,000 | 4,08,000 | - | 4,08,000 |
| 17 | C | District Coordinators to State review meetings | 34 × 3 meetings × 2,500 | 1,70,000 | 85,000 | 2,55,000 |
| 18 | D | State-level training of trainers (District Coordinators and State team) | 50 participants × 3 days × 1,500 | 2,25,000 | - | 2,25,000 |
| 19 | D | District investigator training and observer certification | 34 × 15,000 | 5,10,000 | - | 5,10,000 |
| 20 | D | Steering Committee (6) and Technical Advisory Committee (4) meetings | 10 × 25,000 | 1,75,000 | 75,000 | 2,50,000 |
| 21 | D | DIET workshops to prepare district training-impact profiles | 34 × 10,000 | - | 3,40,000 | 3,40,000 |
| 22 | D | Divisional validation workshops | 4 × 60,000 | - | 2,40,000 | 2,40,000 |
| 23 | D | State validation and dissemination workshop | 1 × 1,50,000 | - | 1,50,000 | 1,50,000 |
| 24 | E | Tablets (retained by DIETs) | 68 × 12,000 | 8,16,000 | - | 8,16,000 |
| 25 | E | Mobile data allowance | 68 investigators × 500 × 9 months | 3,06,000 | - | 3,06,000 |
| 26 | E | Integrated evaluation database and dashboard | Lump sum | 2,50,000 | - | 2,50,000 |
| 27 | E | Tool development (common observation tool, module tests, learning tasks) and pilot in 10 schools | Lump sum | 3,00,000 | - | 3,00,000 |
| 28 | E | Printing of tools, consent and assent forms | Lump sum | 1,50,000 | - | 1,50,000 |
| 29 | E | Qualitative analysis software | Lump sum | 60,000 | - | 60,000 |
| 30 | E | Ethics review | Lump sum | 50,000 | - | 50,000 |
| 31 | F | Report writing, editing, design and printing | 500 copies | - | 3,00,000 | 3,00,000 |
| 32 | F | Framework, policy brief and 34 district profiles (Kannada and English) | 34 × 3,000 + 2 × 50,000 | - | 2,02,000 | 2,02,000 |
| 33 | G | Contingency and administration | 5% of sub-total, rounded | 5,77,500 | 1,26,200 | 7,03,700 |
|  |  | Grand total |  | 1,21,26,400 | 26,49,200 | 1,47,75,600 |

The Principal Investigator is a serving DSERT officer and no salary is charged. Tablets are retained by the DIETs for future evaluation work.

Funding pattern (₹)

Karnataka falls under the 60:40 Centre-State sharing pattern of Samagra Shiksha.

| Period | Central share (60%) | State share (40%) | Total |
| --- | --- | --- | --- |
| Year 1 | 72,75,840 | 48,50,560 | 1,21,26,400 |
| Months 13-18 | 15,89,520 | 10,59,680 | 26,49,200 |
| Total | 88,65,360 | 59,10,240 | 1,47,75,600 |

Proposed release. Funds are sought in phases linked to milestones: the first release on approval; later releases on acceptance of the inception report (M4), the investment and reach report (M7) and the fieldwork report (M11), together with utilisation certificates.

# 17. Monitoring and review

- Quarterly Steering Committee reviews of progress and expenditure.

- Two monitoring visits by the State team to each district; back-checks of 10 per cent of field records and double observation in 10 per cent of classrooms.

- Quarterly physical and financial progress reports to Samagra Shiksha Karnataka; utilisation certificates as per scheme norms.

# 18. Ethics

- Ethics clearance before fieldwork (by Month 3).

- Informed consent from teachers, head teachers and officials; parental consent and child assent for student tasks.

- Observation and test results are used for evaluation only. No individual teacher’s score is shared with supervisors or used for appraisal.

- Student questions on safety are general and age-appropriate; no child is asked about personal experience. Any disclosure is handled through the school’s child protection procedure.

- Teacher and student records are pseudonymised after linkage and handled under the Digital Personal Data Protection Act, 2023.

# 19. Risks and mitigation

| Risk | Mitigation |
| --- | --- |
| Records incomplete or in different formats, especially for 2023-24 | Early data request through Samagra Shiksha Karnataka; district record retrieval; gaps reported openly |
| Teachers cannot be matched across training records | Matching on teacher ID where available, otherwise on name, school and date of birth; match rate reported |
| Overlapping trainings blur the effect of any one training | Comparison by combination and amount of training; module-practice map; prospective cohort |
| Few untrained teachers in some districts | Comparisons pooled at division level; dose-response analysis |
| No major training held in time for the prospective cohort | Cohort drawn from the State training calendar at inception; window for baseline kept open until M8 |
| Teachers change their practice when observed | Research-only use made clear; first 10 minutes not scored |
| Outcome links mistaken for cause | Results reported as associations; triangulated with practice and case-study evidence |
| Partner data not available | Data-sharing agreements with APF and EMTIP before fieldwork |
| Delay in release of funds | Phase-wise release; 5 per cent contingency |

# 20. Expected outcomes and deliverables

- A reconciled database of investment in teacher training, 2022-23 to 2025-26, with an interactive dashboard for DSERT.

- An investment and reach report, including unit costs, groups left out and reasons why approved trainings were not held.

- Evidence on the quality of each cluster of training, on school support, and on transfer to classroom practice and student learning.

- A comparison of the cost-effectiveness of clusters and delivery models, including the cascade and direct models.

- A Karnataka Teacher Professional Development Framework, with recommendations on training load, sequence, mode and follow-up, and inputs for the next PAB proposal and State training calendar.

- 34 district training-impact profiles prepared by the DIETs, and a policy brief in Kannada and English.

- Validated tools (common observation tool, module tests, safety audit, learning tasks) that DIETs can reuse to evaluate future training.

Sustainability. The database and dashboard remain with DSERT and can be updated each year from PAB, PFMS and training MIS records, turning this one-time evaluation into a standing monitoring system. The tools and the experience of DIET faculty remain in the districts.

# 21. Limitations

Teachers were not assigned to training at random, so comparisons are quasi-experimental, and matching adjusts only for characteristics that are measured. Overlapping trainings limit how far the effect of a single training can be separated. Student outcomes are measured once, so links between practice and learning are associations. The district-level analysis rests on 34 districts and is exploratory. The quality of the investment analysis depends on the completeness of the records. Findings apply to Government schools; aided-school teachers who were trained are covered in the desk review only.

# 22. Certificate

Certified that the proposed study does not duplicate any activity approved for the State under Samagra Shiksha or any other scheme of the Government of India; that the costs have been worked out as per scheme norms; and that the funds will be used only for the purpose for which they are sanctioned.

Director
Department of State Educational Research and Training
Bengaluru

# Annexure I: Programme-wise progress, 2022-23 to 2025-26

Compiled from the State’s progress records. Percentages are recomputed from the figures; “-” means not reported.

2022-23

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| English Nali-Kali Levels 1 and 2: teacher training | 1,018 | 1,014 | 99.6 | 13.46 | 11.67 | 86.7 | SSK (PFMS) |
| English Nali-Kali Levels 1 and 2: MRP training | - | - | - | 1.12 | 0.64 | 57.1 | SSK (PFMS) |
| English Nali-Kali 1 and 2: DIKSHA upload | - | - | - | 1.53 | 0.53 | 34.6 | SSK (PFMS) |
| NISHTHA 3.0 online, primary (2021-22, 2nd instalment) | 51,056 | 94,401 | 184.9 | 424.80 | 329.90 | 77.7 | SSK (PFMS) |
| NISHTHA 2.0 online, secondary (2021-22, 2nd instalment) | 58,249 | 54,165 | 93.0 | 439.34 | 387.61 | 88.2 | SSK (PFMS) |
| IISc training | 400 | 395 | 98.8 | 51.00 | 44.47 | 87.2 | EQIP |
| Guruchetana module: face-to-face training | 1,700 | 1,684 | 99.1 | 25.00 | 23.89 | 95.6 | EQIP |
| NIPUN Karnataka training | - | - | - | 159.80 | 44.28 | 27.7 | SSK (PFMS) |
| Total |  |  |  | 1,116.05 | 842.98** | 75.5 |  |

** As recorded; the rows add to 842.99 because of rounding in the source.

2023-24

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Subject-wise training, high school teachers of Classes 9-10 | 10,000 | 10,051 | 100.5 | 250.00 | 240.16 | 96.1 | SSK (PFMS) |
| IISc training | 300 | 322 | 107.3 | 40.00 | 36.94 | 92.4 | EQIP |
| Total | 10,300 | 10,373 | 100.7 | 290.00 | 277.10 | 95.6 |  |

2024-25: primary school teachers

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Marusinchana (Classes 6-7): MRP training | 340 | 321 | 94.4 | 14.00 | 9.15 | 65.4 | SSK (PFMS) |
| Induction MRP training (GPT teachers) | 136 | 136 | 100.0 | 10.40 | 7.99 | 76.8 | TBF |
| Ganitha Ganaka: MRP training | 72 | 72 | 100.0 | 2.88 | 1.50 | 52.1 | K2 |
| English Nali-Kali (Classes 1-3) | 1,195 | 1,146 | 95.9 | 21.51 | 18.18 | 84.5 | SSK |
| Induction training (GPT teachers) | 6,209 | 5,506 | 88.7 | 170.74 | 141.32 | 82.8 | TBF |
| Ganitha Ganaka: teacher training (Classes 3-5) | 34,960 | 32,770 | 93.7 | 114.00 | 78.15 | 68.6 | K2 |
| Marusinchana (Classes 6-7): teacher training | 36,520 | 31,009 | 84.9 | 328.68 | 170.99 | 52.0 | SSK (PFMS) |
| PAB-approved in-service training (Classes 6-8) | 20,767 | 19,430 | 93.6 | 519.15 | 505.35 | 97.3 | SSK (PFMS) |
| Total | 1,00,199 | 90,390 | 90.2 | 1,181.36 | 932.63 | 78.9 |  |

2024-25: high school teachers

| Programme | Phys. target | Achieved | % | Fin. target (₹ lakh) | Spent (₹ lakh) | % | Fund |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Marusinchana (Classes 8-10): MRP training | 344 | 333 | 96.8 | 10.20 | 9.99 | 97.9 | SSK (PFMS) |
| Marusinchana (Classes 8-10): teacher training | 10,034 | 9,169 | 91.4 | 90.30 | 82.46 | 91.3 | SSK (PFMS) |
| PAB-approved in-service training (Classes 9-10) | 9,439 | 8,168 | 86.5 | 235.89 | 227.57 | 96.5 | SSK (PFMS) |
| IISc training (science and mathematics teachers) | 300 | 293 | 97.7 | 43.30 | 38.97 | 90.0 | EQIP |
| Total | 20,117 | 17,963 | 89.3 | 379.69 | 358.99 | 94.5 |  |

2025-26 (as on 31.03.2026): primary school teachers, component F.01.17.01

| Programme (days) | Phys. target | Achieved | % | Fin. target, 1st instalment (₹ lakh) | Released (₹ lakh) | Spent (₹ lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Induction (ICT) and Kalika Deepa (5) | 5,000 | 4,823 | 96.5 | 95.00 | 47.50 | 43.17 |
| POCSO awareness, eradication of corporal punishment, Marusinchana (science and mathematics), Jnana Setu, value education (5) | 51,781 | 42,415 | 81.9 | 491.92 | 457.90 | 363.05 |
| Adivasi residential school teachers (3) | 592 | 155 | 26.2 | 3.37 | 3.37 | 0.41 |
| State-level MRP training: Marusinchana, Jnana Setu, Ganitha Ganaka, Odu Karnataka, Kalika Deepa (5) | 4,511 | 3,864 | 85.7 | 155.63 | 155.63 | 47.55 |
| State-level Nali-Kali MRP training (2) | 1,984 | - | - | 27.38 | - | 0.00 |
| MRP training: POCSO, corporal punishment, value education (3) | 1,984 | 1,902 | 95.9 | 41.07 | 10.51 | 10.99 |
| Training of educational administrators | 1,000 | - | - | 30.00 | - | 0.00 |
| Ganitha Kalika Andolana | 25,891 | 0 | 0.0 | - | - | - |
| Total |  |  |  | 844.37 | 674.91 | 465.17 |

2025-26 (as on 31.03.2026): high school teachers, component F.03.11.01

| Programme (days) | Phys. target | Achieved | % | Fin. target, 1st instalment (₹ lakh) | Released (₹ lakh) | Spent (₹ lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Induction-1, induction refresher and Kalika Deepa (5) | 3,000 | 2,678 | 89.3 | 57.00 | 28.50 | 24.12 |
| Eradication of corporal punishment, POCSO, career counselling awareness, value education, Marusinchana, Jnana Setu (6) | 44,218 | 18,491 | 41.8 | 504.09 | 470.29 | 168.50 |
| BRP/ECO and other trainings for high school teachers (10) | 1,420 | - | - | 26.98 | - | 0.00 |
| Content enrichment, Government school teachers | 44,218 | - | - | - | - | 0.00 |
| Content enrichment, aided school teachers | 23,461 | - | - | - | - | 0.00 |
| Total |  |  |  | 588.07 | 498.79 | 192.62 |

2025-26 (as on 31.03.2026): component F.01.22.02

| Programme (days) | Phys. target | Achieved | % | Fin. target, 1st instalment (₹ lakh) | Released (₹ lakh) | Spent (₹ lakh) |
| --- | --- | --- | --- | --- | --- | --- |
| Induction training (elementary) | 12,600 | 11,515 | 91.4 | 315.00 | 119.70 | 92.59 |
| Odu Karnataka (1), Ganitha Ganaka (½) and value education (½) | 51,919 | 49,584 | 95.5 | 519.19 | 197.29 | 178.00 |
| Odu Karnataka (1) | 23,010 | - | - | 259.60 | - | 0.00 |
| Total |  |  |  | 1,093.79 | 316.99 | 270.59 |
| Grand total, 2025-26 |  |  |  | 2,526.23 | 1,490.69 | 928.38 |

SSK: Samagra Shiksha Karnataka; PFMS: Public Financial Management System; EQIP: grant as recorded in the source; K2 and TBF: fund codes as recorded in the source, to be mapped to scheme heads in Component 1.

# Annexure II: Data discrepancies found in the progress records

| No. | Record | Discrepancy | Action in this study |
| --- | --- | --- | --- |
| 1 | 2023-24, subject-wise training, Classes 9-10 | Physical achievement reported as 110.65%; the figures (10,051 of 10,000) give 100.51% | Recompute all percentages from source figures |
| 2 | 2023-24, IISc training | Financial achievement reported as 87.20% (the same as in 2022-23); the figures (₹36.94 lakh of ₹40.00 lakh) give 92.35% | Verify against PFMS |
| 3 | 2022-23, NISHTHA 3.0 (primary) | 94,401 trained against a target of 51,056 (184.9%) | Count unique teachers from DIKSHA records |
| 4 | 2025-26, MRP training on POCSO, corporal punishment and value education | Expenditure (₹10.99 lakh) exceeds funds released (₹10.51 lakh) | Reconcile release and expenditure |
| 5 | 2025-26, high school induction | Recorded as “9 days + 1 day (total 5 days)” | Confirm the actual duration |
| 6 | 2023-24, all programmes | Only two programmes are reported for the year | Obtain the full PAB-approved list |

# Annexure III: Programme inventory by cluster

Figures are as recorded in the State’s progress records (Annexure I) or as reported by the programme. All figures will be verified in Component 1.

| Cluster | Programme | Years recorded | Source of figures |
| --- | --- | --- | --- |
| A | NISHTHA 2.0 and 3.0 (online) | 2022-23 | Annexure I |
| A | English Nali-Kali | 2022-23, 2024-25 | Annexure I |
| A | IISc training | 2022-23 to 2024-25 | Annexure I |
| A | Guruchetana module | 2022-23 | Annexure I |
| A | NIPUN Karnataka training | 2022-23 | Annexure I |
| A | Subject-wise and PAB-approved in-service training (Classes 6-10) | 2023-24, 2024-25 | Annexure I |
| A | Marusinchana (Classes 6-10) and Jnana Setu | 2024-25, 2025-26 | Annexure I |
| A | Ganitha Ganaka, Odu Karnataka, Kalika Deepa | 2024-25, 2025-26 | Annexure I |
| A | Induction training (elementary and high school) | 2024-25, 2025-26 | Annexure I |
| A | Content enrichment; Ganitha Kalika Andolana | 2025-26 (not started) | Annexure I |
| B | POCSO, eradication of corporal punishment, value education, career counselling | 2025-26 | Annexure I |
| B | Child rights; road safety | To be confirmed | Programme records |
| C | TALP induction (about 18,600 teachers) and refresher (about 2,000 teachers) | To be confirmed | TALP programme |
| C | Digital Library training | To be confirmed | Programme records |
| D | Azim Premji Foundation partnership (about 10,000 teachers) | To be confirmed | APF |
| D | EMTIP bilingual schools | To be confirmed | EMTIP programme |

# Annexure IV: References

- Banerjee, A., Banerji, R., Berry, J., Duflo, E., Kannan, H., Mukerji, S., Shotland, M. and Walton, M. (2017). From proof of concept to scalable policies: Challenges and solutions, with an application. Journal of Economic Perspectives, 31(4), 73-102.

- Darling-Hammond, L., Hyler, M. E. and Gardner, M. (2017). Effective Teacher Professional Development. Palo Alto, CA: Learning Policy Institute.

- Desimone, L. M. (2009). Improving impact studies of teachers’ professional development: Toward better conceptualizations and measures. Educational Researcher, 38(3), 181-199.

- Guskey, T. R. (2000). Evaluating Professional Development. Thousand Oaks, CA: Corwin Press.

- Guskey, T. R. (2002). Does it make a difference? Evaluating professional development. Educational Leadership, 59(6), 45-51.

- Kennedy, M. M. (2016). How does professional development improve teaching? Review of Educational Research, 86(4), 945-980.

- Kraft, M. A., Blazar, D. and Hogan, D. (2018). The effect of teacher coaching on instruction and achievement: A meta-analysis of the causal evidence. Review of Educational Research, 88(4), 547-588.

- Popova, A., Evans, D. K., Breeding, M. E. and Arancibia, V. (2022). Teacher professional development around the world: The gap between evidence and practice. World Bank Research Observer, 37(1), 107-136.

- Stufflebeam, D. L. and Zhang, G. (2017). The CIPP Evaluation Model: How to Evaluate for Improvement and Accountability. New York: Guilford Press.

- World Bank. Teach: Classroom Observation Tool. Washington, DC: World Bank.

- Ministry of Education (2020). National Education Policy 2020. Government of India.

- Ministry of Education. Samagra Shiksha: Framework for Implementation. Government of India.

- Ministry of Education (2021). NIPUN Bharat Guidelines. Government of India.

- NCERT. National Achievement Survey 2021; PARAKH Rashtriya Sarvekshan 2024. New Delhi: NCERT.

- NCERT (2023). National Curriculum Framework for School Education 2023. New Delhi: NCERT.

- NCTE. National Professional Standards for Teachers. New Delhi: NCTE.

- Government of India. Protection of Children from Sexual Offences Act, 2012; Right of Children to Free and Compulsory Education Act, 2009; Digital Personal Data Protection Act, 2023.